| OFFICE OF REAL PROPERTY TAX SERVICES Name (optional) Region Regional Director (Optional) |  |  |
| --- | --- | --- |

[Delete this page before issuing the RFP.]

Date

Mr./Ms. XXXXX, Mayor/Supervisor,

Mr./Ms. XXXXX, Assessor

City/Town of XXXXX

XX XXXXX XX

XXXXX, NY XXXXX

Dear Mr./Ms. XXXXX:

Thank you for requesting or downloading our template for a Request for Proposal (RFP) for reassessment services to be provided by a contractor.

The responsibility for defining the products and services to be received from any contractor, as well as the time frame for the delivery of those products and services, rests with the issuing municipality.  Since the RFP will serve as the basis for any subsequent contractual agreement between a municipality and a contractor, great care should be taken in the customization of the RFP so that desired services, dates of delivery and consequences where stated service levels and/or delivery dates are not met are precisely and clearly defined.  The RFP issued by your municipality should only reflect those services actually desired – the services for which your municipality is willing to pay – as this will directly influence the project’s cost.

Within the body of this RFP template, you will note [bracketed bold italicized language in blue].  These statements are intended to offer guidance to those officials working to customize this template.  This language should be removed prior to the issuance of the RFP as its inclusion may prove confusing to a contractor looking to respond.  The page numbers in the Table of Contents should be updated using the proper menu options once the local customization of this document is complete.

The goal of the Office of Real Property Tax Services is to assist your municipality to ensure that your reassessment is conducted appropriately and implemented successfully.   As a start to this process, we strongly recommend you contact your ORPTS’ regional office for assistance in customizing this RFP.

We look forward to working with your municipality to implement a successful reassessment!

Tips for Customizing this Document

[Delete this page before issuing the RFP.]

All sections of this template should be included in the RFP to be issued with the possible exception of Section Four.  All sections of this template will require further customization.  Portions of Section Four may be eliminated based on the scope of services desired and the nature of the municipality’s project.  The municipality will need to determine which major property types, if not all, are the subject of this project, i.e., residential, commercial, vacant, etc.

Your municipality’s project will, in all likelihood, fit one of the project scenarios below:

Data Collection only:

Pay special attention to sections 4.1 through 4.10

Data Verification and Valuation Services:

Pay special attention to sections 4.1 through 4.4 and 4.10 through 4.23

Valuation Services only (municipality deems its existing inventory to be adequate as is):

Pay special attention to sections 4.10 through 4.23

Complete project – full Data Collection and Valuation Services (initial reassessment):

Pay special attention to all of Section Four

Updating the Table of Contents

Once this template has been modified and all “guidance” language has been removed, the Table of Contents (TOC) will no longer be accurate. It is suggested that the user take advantage of Word “Help” to learn how to update the TOC.  If the changes are minimal, the TOC can be updated as follows:

- Save the document

- Right-click anywhere in the TOC – the entire content block goes gray

- Click “Update Field” on the menu that appears

- Select “Update entire table” on pop-up

- Click “Okay”

- Save the document

[Delete this page before issuing the RFP and updating the Table of Contents.]

REQUEST FOR PROPOSAL

SPECIFICATIONS

Real Property Reassessment Project

MUNICIPALITY

NEW YORK

Prepared By:						Date:

TO WHOM IT MAY CONCERN

[Preparers of this RFP should discuss the selection process with their municipal attorney to ensure agreement that this project would be considered professional services and the selected vendor does not necessarily have to be the lowest bidder.]

Enclosed are specifications for the contractual services phase of the Municipality’s reassessment program.  Companies interested in providing these services are invited to attend a pre-proposal conference at Site.  The conference is intended to provide clarification of these specifications, where needed, and to respond to all technical inquiries.  All questions concerning these specifications shall be presented at the pre-proposal conference or mailed to Name/Address prior to the pre-proposal conference.  All companies that receive this RFP will also receive the summary of the pre-proposal conference and / or all written inquiries along with answers.  No subsequent inquiries will be accepted.

Companies desiring to provide services according to these specifications must deliver    #    sealed copies of their proposal to Name/Address no later than Time & Date. Proposals received after this specified time will not be considered by the municipality.

All company proposals must be formatted as specified in Appendix D.  [Municipality should specific format of submission – is electronic submission acceptable?  Municipality should consider email confirmations of proposal received.]  Full proposals, with a restating of the RFP sections and specifications, are not acceptable. These specifications are considered the minimum standards for this project.  The only acceptable deviations from the specifications are responses in excess of those specified and must be explained in detail in the proposal.  No substantive changes will be allowed after the submission of the proposals.  The pre-proposal conference scheduled for xx/xx/xx is important and firms are encouraged to have their prospective project directors attend.  Interviews will be held for companies that submit proposals at the discretion of the municipality.  Proposal clarification and explanation will be the primary purpose of the interview; therefore companies are encouraged to have their prospective project directors actively participate in this process.

PROPOSAL PROCESS SCHEDULE

[Time frames noted below are simply general suggestions.  The time allowed for the proposal process will vary depending on the time available between the decision to develop an RFP and the roll year for which the project is to be implemented.  Ensure that the proposal process schedule and project time line have sufficient time built in for the anticipated contract negotiations.]

| Event | Date | Time |
| --- | --- | --- |
| Issue RFP | xx/xx/xx | N/A |
| Receipt of Inquiries from Companies No Later Than... [30 days after RFP is issued] | xx/xx/xx | xx:xx p.m. |
| Pre-proposal Meeting [45 days after RFP is issued] | xx/xx/xx | xx:xx a.m. |
| Issue Pre-proposal Meeting Summary [60 days after RFP is issued] | xx/xx/xx | N/A |
| Receipt of Sealed Proposals [75 days after RFP is issued] | xx/xx/xx | xx:xx a.m. |
| Conduct Company Interviews Week of... [within 90 days after RFP is issued] | xx/xx/xx | N/A |
| Announcement of Most Responsive Bidder [within 105 days after RFP is issued] | xx/xx/xx | N/A |
| Selection of Most Responsive Bidder | xx/xx/xx | N/A |
| Contract Negotiations | xx/xx/xx - xx/xx/xx | N/A |
| Contract Award [within 180 Days after RFP is issued] | xx/xx/xx | N/A |

CHOOSE ONE

Single Municipality

The municipality assumes no liability for the costs incurred by a company in preparing its proposal for professional services in response to this RFP.  The municipality reserves the right to reject any or all proposals.  Companies that have submitted acceptable responses will be notified of contractor selection by letter after the final determination has been made. The municipality intends that, if a contractor is chosen, an instrument of contract will be signed no later than Date.

Consortium - One contract with one price with potential optional services by individual municipalities

The consortium assumes no liability for the costs incurred by a company in preparing its proposal for professional services in response to this RFP.  The consortium reserves the right to reject any or all proposals.  All company proposals must include a single Project Cost Itemization table representing the entire project.  It will be the company’s / consortium's responsibility to allocate each municipality's share of all project costs on a per-parcel basis.  Companies that have submitted acceptable responses will be notified of contractor selection by letter after the final determination has been made.  The consortium intends that, if a contractor is chosen, a sole instrument of contract will be signed with the consortium (representing the participating municipalities) no later than Date.

Consortium - Multiple contracts with one price

The consortium assumes no liability for the costs incurred by a company in preparing its proposal for professional services in response to this RFP.  The consortium reserves the right to reject any or all proposals.  All company proposals must include a single Project Cost Itemization table representing the entire project.  It will be the company’s / consortium's responsibility to allocate each municipality's share of all project costs on a per-parcel basis.  Companies that have submitted acceptable responses will be notified of contractor selection by letter after the final determination has been made.  The consortium intends that, if a contractor is chosen, an instrument of contract will be signed with each participating municipality no later than Date.

Consortium - Multiple contracts with multiple prices

The consortium assumes no liability for the costs incurred by a company in preparing its proposal for professional services in response to this RFP.  The consortium reserves the right to reject any or all proposals.  All company proposals must include a Project Cost Itemization table for each participating municipality.  Companies that have submitted acceptable responses will be notified of contractor selection by letter after the final determination has been made.  The consortium intends that, if a contractor is chosen, an instrument of contract will be signed with each participating municipality no later than Date.

Firms that have been selected as finalists will be notified by letter. The municipalities / consortium intend that, if a firm is chosen, contract negotiations will be completed in an expeditious manner.  The selected firm will be determined by its experience, the cost of the proposal, response to technical specifications and references.

Table of Contents

GLOSSARY OF TERMS	9

SECTION 1 - INTRODUCTION	14

SECTION 2 - PROFILE OF MUNICIPALITY	16

MUNICIPAL SUMMARIES – Property Type/Responsibility Grid	20

SECTION 3 - GENERAL RESPONSIBILITIES - MUNCIPALITY AND ORPTS	21

3.1	Municipality	21

3.1.1  Project Management	21

3.1.2  Data Manager	21

3.1.3  Staff Involvement	21

3.1.4  Documentation	21

3.1.5  Space and Equipment	22

3.1.6  Property Record Cards	23

3.1.7  Assessor’s Participation	23

3.1.8  Clerical Function(s)	23

3.1.9  Application for Advisory Appraisal	23

3.1.10  GIS Capacity and Availability	24

3.1.11  Software, if other than RPS.	24

3.1.12  Payments to Contractors	24

3.2	ORPTS	24

3.2.1  Software	24

3.2.2  Data Collection Material	24

3.2.3 Processing Fees	24

3.2.4  Advisory Appraisals	25

3.2.5  General	25

SECTION 4 - PROJECT REQUIREMENTS/CONTRACTOR RESPONSIBILITIES	26

4.1	Project Management	26

4.2	Project Timetable	26

4.3	Public Information	29

4.4	Local Staff Training	30

4.4.1  Data Collector Training	31

4.4.2  Training of Municipality Staff & Local Assessor	31

4.4.3  Board of Assessment Review Training	32

4.5	Data Processing	32

4.5.1  Hardware	32

4.5.2  Software	32

4.5.3  Scheduling	32

4.6	Tax Map Data	33

4.7	Property owner Inquiry	33

4.8	Subject Inventory Data Collection	33

4.8.1  Verification and Collection	33

4.8.2  Collection Instrument	34

4.8.3  Parcel Entry	34

4.8.4	File Creation and Maintenance	35

4.8.5  Parcel Improvement Sketches	36

4.8.6  Data Collectors	36

4.8.7  Data Quality Control	37

4.8.8  Vacant and Agricultural Land	37

4.8.9  Public Utility Parcels and Ceiling Railroad Parcels	37

4.8.10  Property Description Report (also known as Data Mailer)	38

4.8.11  Photography/Image	38

4.9	Sales Inventory Collection and File Creation	39

4.10	Data Edits	39

4.11	Valuation	40

4.11.1  Residential/Farm/Vacant	40

4.11.2  Commercial/Industrial	40

4.11.3  Unique and Highly Complex Parcels	41

4.11.4 Condominiums and Cooperatives (as applicable)	41

4.11.5 Valuation Reports	42

4.12	Field Review	42

4.13	Assessor’s Value Review	43

4.14	Assessment Disclosure Processing / Tax Shift Analysis	43

4.15	Informal Review Process	44

4.16	Value Change Notice (Section 511 Notice)	44

4.17	Formal Defense of Values	44

4.18	Project Status Control	45

4.19	Submissions for State Aid/Value Verification	45

4.20	Mass Mailing and Postage	45

4.21	Data Entry	46

4.22      Valuation Documentation	46

4.23	Option - Updating of All Values for the Post-Reassessment Year Roll	46

SECTION 5 - DATA SECURITY	47

SECTION 6 - CONTRACTOR PROJECT STAFFING	48

6.1	Project Management and Technical Staff	48

6.2	Staffing Changes	48

SECTION 7 - DELIVERABLE PRODUCTS	49

SECTION 8 - PAYMENT SCHEDULE AND PENALTY	52

SECTION 9 - CONTRACTUAL REQUIREMENTS	53

9.1	Rules and Procedures	53

9.2	Employment Requirements	53

9.3	Changes in Contract	53

9.4	Statement of Non-collusion	54

9.5	Insurance Requirements	54

9.6	Conflict of Interest	55

9.7	Assignment of Contract	55

9.8	Compensation	55

9.9	Ownership of Work Products	55

9.10	General Legal Responsibility	55

9.11	Instrument of Contract	55

9.12 	Disputes - Venue and Jurisdiction	56

SECTION 10 - PROJECT COST ITEMIZATION	57

APPENDIX A – Municipality Code of Ethics	58

APPENDIX B – Unique or Highly Complex Parcel List	59

APPENDIX C – Affidavit	60

APPENDIX D – Sample Proposal	61

APPENDIX E – Company Proposal Response Grid	64

APPENDIX F – Assessor’s Sign-off Documents	65

APPENDIX G – Sample Forms Preferred by Municipality	71

Attachment: Volume 9 - Opinions of Counsel SBEA No. 4	72

Attachment: IAAO Mass Appraisal Revaluation Template (adapted)	74

GLOSSARY OF TERMS

The following terms are used throughout these specifications and shall have that meaning expressly indicated below:

- ASSESSOR - The individual or the Board of Assessors serving as the Assessor in the municipality.

- COD - Coefficient of Dispersion - The average deviation of a group of numbers from the median expressed as a percentage of the median.  In ratio studies, the average percentage deviation from the median ratio. - IAAO, Standard on Ratio Studies, April 2013.

- COMPANY - A qualified firm that submits a formal proposal in response to these specifications.

- COMPUTER-ASSISTED MASS APPRAISAL (CAMA) - A procedure by which values are estimated for parcels by means of computer-based calculations incorporating statistical methods where appropriate.  Residential parcels are often valued by the sales approach, utilizing multiple regression analysis (MRA) or the adaptive estimation procedure (AEP), and direct sales comparison to the most comparable properties, as well as through the cost approach, utilizing land schedules, cost tables, and depreciation information.  Vacant land parcels are valued through land schedules that are derived by MRA or AEP models of comparable land sales.  Commercial, industrial, and utility properties are usually valued through direct sales comparison using cost-based, income-based, and market-based value per-unit data, as available and appropriate.  Data adequacy and accuracy are key considerations in developing CAMA estimates.  For reliable results, use of data from outside the assessing unit may be necessary in the case of smaller assessing units and/or less-numerous types of property.

- CONSORTIUM - A group of municipalities entering into a cooperative effort to undertake a municipal-wide reassessment project using the same contractor.

- CONTRACT ADMINISTRATOR - The municipal official who represents the municipality in all legal matters with regard to this project.

- CONTRACTOR / VENDOR- The company or consultant that enters into an agreement with the municipality to provide the professional contract services described in these specifications.

- CREW CHIEF - (field supervisor(s)) the person(s) responsible for the recollection and/or field verification of data collected by the data collectors.  The crew chief monitors and ensures the quality, consistency and accuracy of all of the data.  The crew chief must be trained as a data collector and have a minimum of six months of prior experience as a data collector.  In addition, the crew chief must demonstrate  X   years experience in the assessment or appraisal field, or two years of experience working with a reassessment firm as a data collector or appraiser.  [Does the municipality wish to make the qualifications required for crew chiefs more / less restrictive or specify particular qualifications?]

- CYCLICAL REASSESSMENT PLAN - The municipality’s program for conducting municipal-wide reappraisals in which each parcel is reappraised individually at least once every four years and all parcels are physically inspected at least once every six years.  The cyclical plan template can be found on the DTF website: http://www.tax.ny.gov/pdf/current_forms/orpts/rp1573acrp_fill_in.pdf

- DATA COLLECTOR - An individual responsible for the field collection and recording (on the appropriate ORPTS’ data collection document) of real property valuation data.  The data collector must have completed a program of training that includes, at a minimum, "Fundamentals of Data Collection, R/F/V" and must demonstrate  X   years experience in the assessment or appraisal field, or two years of experience working with a reassessment firm as a data collector or appraiser.  [Does the muni wish to make the qualifications required for data collectors more / less restrictive or specify particular qualifications for certain property types?  To achieve potential cost savings, does the municipality want to specify that a certain percentage of the data collectors meet the data collector criteria in the RFP and the remaining percentage consist of college graduates, realtors, home inspectors, or others with equivalent knowledge and experience?]

- DATA MAILER - A computer-generated report listing, enumerating and describing selected data elements.

- FIELD REVIEW - The process of identifying market value through the review of appropriate valuation documentation from the public right-of-way.

- FIELD REVIEWER - The individual with experience and knowledge of valuation techniques employed on this project for the property categories for which he/she will be responsible.  A field reviewer must have completed the same training as required for a data collector.  For an R/F/V field reviewer, the individual must either have prior field review experience of at least 1,000 parcels or have trained with an experienced field reviewer for a minimum of 1,000 parcels.  For all other categories, the individual must have additional training and experience beyond the R/F/V experience stated subject to the applicable requirements of the municipality.

[Does the muni wish to make the qualifications required for field reviewers more / less restrictive or specify particular qualifications for reviewers of particular property types?]

- FINAL ASSESSMENT ROLL - A document containing assessment and exemption information on all parcels in a municipality.  It differs from the tentative assessment roll with respect to changes ordered by a Board of Assessment Review, assessments and ceilings made by the State Board and ownership and address changes since the tentative roll.  It is filed on MM/DD in the Town / City of                .

- MUNICIPALITY - The Town/City of                   .

- NYS DTF – The New York State Department of Taxation and Finance.

- ORPTS - The Office of Real Property Tax Services, a division of the New York State Department of Taxation and Finance.

- ORTHO-PHOTOGRAPHY - An ORTHOPHOTO, ORTHOPHOTOGRAPH or ORTHOIMAGE is an aerial photograph geometrically corrected ("orthorectified") such that the scale is uniform: the photo has the same lack of distortion as a map.  Unlike an uncorrected aerial photograph, an orthophotograph can be used to measure true distances because it is an accurate representation of the Earth's surface, having been adjusted for topographic relief, lens distortion, and camera tilt.

- OBLIQUE AERIAL PHOTOGRAPHY - Photographic images taken from an aircraft where the camera direction is at an angle to the ground beneath.

- PARCEL - A separate, tax map-designated, assessed lot, parcel, piece or portion of real property.

- PRELIMINARY ROLL - A roll with assessed values and exempt amounts subject to informal review by a property owner with the Assessor and subject to change prior to Tentative Roll.

- PRD - Price-Related Differential - The mean divided by the weighted mean.  The statistic has a slight bias upward.  Price-related differentials above 1.03 tend to indicate assessment regressivity; price-related differentials below 0.98 tend to indicate assessment progressivity. - IAAO, Standard on Ratio Studies, April 2013.

- PROJECT - The overall effort, including the activities of all participants.

- PROJECT ADMINISTRATOR - The municipal official responsible for overall project management and analysis and direct project coordination, who represents the municipality in all contract administrative matters.

- PROJECT DIRECTOR - The contractor staff member who will be responsible for contractor project management and coordination of all contractor activities, who will represent the contractor in all contract administrative matters.

[If multiple municipalities are involved, can there be multiple project directors and/or other staff or does the consortium prefer a single project director?]

- PROJECT MONITOR – A consultant hired by the municipality(ies) who will be responsible for quality control of the contractor’s work on behalf of the Assessor / municipality in the context of the contract signed.

- RFP - This request for proposal which contains specifications for the contractual services phase of the municipality's reassessment project and serves as the senior document: the basis for resolving disputes.

- RPS - The New York State Real Property System which is an assessment administration system with Computer-Assisted Mass Appraisal (CAMA) capabilities.

- RATIO STUDY - A ratio study is an analysis of the relationship between assessments and market value (i.e., assessment ratio) for those parcels where a recent market value indicator - a sale or an independent appraisal - is available.  The study utilizes the assessment ratio data and applicable statistical methods to determine the overall or average percentage of current market value the assessments represent.  The ratio study may also measure the extent to which the average assessment ratio is changing over time thus quantifying the assessment adjustment necessary to maintain current market conditions.  The statistical methods and indicators used in the study include measures of central tendency (mean, weighted mean, median); measures of variation (coefficient of dispersion, coefficient of variation, price-related differential); measures of association (multiple regression, correlation); and significance tests (binomial test, Z-test).

  - IAAO, Standard on Ratio Studies, April 2013.

- REAPPRAISAL - The process of physically inspecting and reappraising each parcel.  Reappraisal refers to the valuation of a single parcel.

  - Physically inspecting – at a minimum, observing each property from the public right-of-way in order to ascertain that the physical characteristics necessary for reappraising are complete and accurate.  On-site inspections are recommended to maximize data accuracy.

  - Reappraising – developing and reviewing a new determination of market value for each parcel, based on current data, by the appropriate use of one or more of the accepted three approaches to value (cost, market, and income).*

*ORPTS “Guidelines for Cyclical Reassessment”:

http://www.tax.ny.gov/research/property/assess/state_aid/cyclical_guidelines.pdf

- REASSESSMENT - A systematic review of the assessments of all locally assessed properties, either within an assessing unit or within a class of a special assessing unit, to assure they are at the stated uniform percentage of value as of the valuation date of the assessment roll upon which the assessments appear.  It is synonymous with the terms revaluation and update. A reassessment can be completed by a reappraisal of parcels, trending of parcels to current value, or a combination of both. The use of trending as the sole means of establishing a new market value for any parcel will not be considered a reassessment for the purpose of satisfying State aid criteria in a reappraisal year as part of a plan for cyclical reassessment. *

*ORPTS “Guidelines for Cyclical Reassessment”:

http://www.tax.ny.gov/research/property/assess/state_aid/cyclical_guidelines.pdf

- RPTSA – The Real Property Tax Services Agency of _____ County whose agency head is the County Real Property Tax Director or equivalent title.

- RULES - The New York State Codes, Rules and Regulations for Real Property Tax Administration that established standards of certification for state financial reimbursement (20 NYCRR).  The Rules that must be adhered to are those in force as of the date of contract execution.

- STATE BOARD / SBRPTS - The New York State Board of Real Property Tax Services.

- STREET LEVEL PHOTOGRAPHY – Images of whatever can be seen from a public right-of-way.

- SYSTEMATIC ANALYSIS - The four-step process of reassessment which includes the gathering and grouping of data and information, application of accepted analytical techniques both diagnostic and prescriptive and the subsequent validation of results before the filing of a tentative roll.

- TAXABLE STATUS DATE - The ownership and physical condition of real property as of this date are assessed according to a value fixed as of the valuation date in the year that the reassessment is to be implemented.  For the Town / City of               , the taxable status date is    MM/DD   .

- TENTATIVE ASSESSMENT ROLL - A preliminary assessment roll the assessed values and exempt amounts on which are subject to grievance by a property owner before a Board of Assessment Review. The roll does not become final until this Board has acted upon all grievances.  The tentative assessment roll filing date for the Town / City of                is   MM/DD   .

- TRENDING - The process of applying factors based upon criteria such as property type, location, size, and age, developed from assessment-sales ratio studies or other market analysis, to groups of properties to maintain uniformity of assessments at the stated uniform level of assessment.  The use of trending as the sole means of establishing a new market value for any parcel will not be considered a reassessment for the purpose of satisfying State aid criteria in a reappraisal year as part of a plan for cyclical reassessment. *

*ORPTS “Guidelines for Cyclical Reassessment”: http://www.tax.ny.gov/research/property/assess/state_aid/cyclical_guidelines.pdf

- UNIFORM ASSESSMENT STANDARDS - a general blueprint for local governments assessing units to establish "equitable" and "transparent" assessments. "Equitable" means that all properties are uniformly assessed at full market value.  "Transparent" means that the system is easy to understand by all taxpayers and that all relevant information is readily available to the public. The Uniform Assessment Standards can be found on the DTF website: http://www.tax.ny.gov/research/property/reports/ratio/uniformassmntstd/index.htm

- VALUATION - The process of estimating market values for all parcels in the municipality using mass appraisal procedures which are in compliance with standard 6 of the Uniform Standards of Professional Practice of the Appraisal Foundation.

- VALUATION DATE - All real property is valued as of this date. For the Town / City of                it is    MM/DD   of the preceding year.

- VERIFIED PARCEL - A parcel for which the inventory data has been field verified for completeness, corrections entered onto the inventory file, file edited by computer and corrected for any errors.

- WORK/WORK PRODUCTS - The services to be performed/delivered by the contractor.

SECTION 1 - INTRODUCTION

This reassessment of all real property is the result of a decision made by this (these) municipality(ies) to achieve equitable assessments.  It is to be conducted pursuant to Sections 301 and 305 of the New York State Real Property Tax Law (RPTL).  It is the intent of the municipality to complete the reassessment in accordance with section 1573 RPTL, rules and procedures in order to qualify for State Aid.

This document is a request for proposal for the reassessment of all real property except Roll Section 5 (special franchise) within the municipality.  The contractor will be required to value all locally assessed parcels in:

- Roll Section 1 (taxable)

- Roll Section 3 (state owned land)

- Roll Section 7 (ceiling railroad)

- Roll Section 8 (wholly exempt)

[The municipality should clearly state If any of the roll sections listed above are not to be considered the responsibility of the contractor.]

Additionally, the contractor may also value and / or review and incorporate any ORPTS’ provided values, e.g., special franchise, ceiling railroad, and / or utility advisory appraisals.  For Roll Section 6, public utility property, the contractor will provide values for all land.  Advisory appraisals will be requested (from ORPTS' Valuation Services Bureau) for utility properties (Roll Section 6) and forestry factors and assistance (from the State Forestry Unit). [The municipality should clearly note those utility parcels, if any, for which it consciously will not request advisory appraisals from ORPTS.]  Advisory appraisals requested for industrial and complex commercial properties may be requested from the ORPTS’ regional office.   There is no guarantee, however, such advisory appraisals will be provided due to ORPTS’ staffing and budget considerations.  So, companies will be required as part of their proposal to itemize a separate add-on price for valuation of structural and non-structural public utility property (Roll Section 6) in the event ORPTS cannot provide advisory appraisals.

This proposal will specify the system(s) that will be used to accomplish its goal of placing values at a uniform percent of full market value on the year tentative assessment roll.  The municipality intends that this project conform to the Rules (20NYCRR).  A copy of the most current, applicable Rules can be obtained by contacting the ORPTS Regional Services Bureau, State Aid Representative, at:

Address_________________________________, Phone_______________________.

This information is also available through the DTF website at: http://www.tax.ny.gov/research/property/assess/state_aid/index.htm

A statement of the company's intention to fully comply with these Rules must be included in each proposal.

The municipality intends to solicit proposals from companies capable of undertaking and successfully completing a reassessment of approximately    # [Equal to or Exceeding Total Parcel Count] parcels of real property over a    #    month period, and conducting such reassessment in conformance with the Rules. The municipality intends to select a company that has a successful history of undertaking and completing real property reassessment projects with a preference to those cost effectively and efficiently using the latest industry accepted technology.

Therefore, the company must have undertaken and completed real property reassessment projects of which any one such project must have totaled over    #    parcels.  In addition, the company must have qualified personnel on its permanent payroll staff who have direct experience managing real property reappraisal projects and who have the skills and experience to undertake major public information and personnel training programs.

Supplemental technical experience information, relating only to real property reassessment projects, is required in the proposal.  Such information shall include full identification of the contracting parties, number of parcels, dates and duration of contracts, use of the NYSRPS and / or applicable software and compliance with the Rules.  The company is required to submit in its proposal a complete client list of all real property related projects with which it has been associated over the past    #     years.  [Typically five years, but could be more or less.]  A contact person and telephone number is to be provided for each project listed.

Appendix D outlines a format for the proposal and items that it must contain.  Proposals that deviate from the format or contents may not be considered.

The RFP is the minimum specification for the project.  Each proposal must contain a statement that the company fully intends to comply with the specifications as found in this RFP.  In no event does this preclude a company from offering goods and/or services above and beyond those specified in the RFP.

Finally, this document is in compliance with the Uniform Standards of Professional Appraisal Practice (standard 6) developed by the Appraisal Foundation for Mass Appraisal.

SECTION 2 - PROFILE OF MUNICIPALITY

The municipality(ies) is (are) located in the County of   NAME  , New York.

A detailed municipal summary is contained on the following page.  There is also an abundance of information available on the ORPTS’ website to assist the contractor in gathering pertinent information.  In addition, a municipal profile can be provided by ORPTS’ regional office upon request.

- additional descriptions;

- previous reassessments;

- NYSRPS and / or other applicable software experience;

- current staffing and operations; and

- data processing/administration resources

| ITEM | QUANTITY |
| --- | --- |
| Population |  |
| Number of School Districts |  |
| Number of Special Districts |  |
| Square Miles (Area) |  |
| Current Equalization Rate |  |
| Residential Assessment Ratio |  |
| Homestead \ Non homestead Classified Roll | / |
| Parcels with negotiated settlements |  |
| Number of Property Transfers / Year (RP-5217's) |  |
| Outstanding Building Permits |  |
| Software | Name / Level |
| Office Productivity Software Suite |  |
| Assessment Administration Software |  |
| Computer-Assisted Mass Appraisal Software |  |
| Tax Billing & Collection Software |  |
| Geographic Information System Software |  |
| Oblique Aerial Photography Software |  |
| Street Level Photography Software |  |

Year of last reassessment for each municipality

Year of last data collection for each municipality

Is there a possibility the municipality intends to apply for Approved

Assessing Unit status in order to adopt Article 19 (Homestead)?	            		Yes / No

The resulting values arrived at upon the completion of reassessment

services will serve as the basis for assessments implemented for the  year

Tentative Assessment Roll filed on MM/DD/YYYY with the MM/DD/YYYY

Valuation Date and MM/DD/YYYY Taxable Status Date.

Describe any specialized valuation tasks that will be encountered in

the municipality (e.g., parcels with water frontage, NYC

Watershed properties, large parcels meeting the definition

of RPTL 805 and / or 1316, estates, specific wholly exempt properties, etc.).

MUNICIPAL SUMMARIES – Property Class/Roll Section Breakdown						Table 1A  #1 OF ?

[For all municipalities in total, e.g., a Consortium, and each individual municipality]

TOWN OF XXXX    SWIS - XXXX

20XX FINAL ASSESSMENT ROLL

|  | NUMBER OF PARCELS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PROPERTY CLASS CODE USE | Roll Section 1 | Roll Section 3 | Roll Section 5 | Roll Section 6 | Roll Section 7 | Roll Section 8 8RRRR | Totals |
| 100 Agricultural |  |  |  |  |  |  |  |
| 200 Residential |  |  |  |  |  |  |  |
| 300 Vacant Land |  |  |  |  |  |  |  |
| 400 Commercial, Except Condos |  |  |  |  |  |  |  |
| 400-C Commercial Condos |  |  |  |  |  |  |  |
| 500 Recreation |  |  |  |  |  |  |  |
| 600 Commercial Service |  |  |  |  |  |  |  |
| 700 Industrial |  |  |  |  |  |  |  |
| 800 Public Service |  |  |  |  |  |  |  |
| 900 Wild & Forest Lands |  |  |  |  |  |  |  |
| TOTAL ASSESSMENT ROLL |  |  |  |  |  |  |  |

A breakdown of the number of properties with water frontage by major property type will appear as part of Appendix B.

MUNICIPAL SUMMARIES – Residential Property Class Breakdown						Table 1B   #1 OF ?

[For all municipalities in total, e.g., a Consortium, and each individual municipality]

TOWN OF XXXX    SWIS - XXXX

20XX FINAL ASSESSMENT ROLL

|  | NUMBER OF PARCELS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PROPERTY CLASS CODE USE | Roll Section 1 | Roll Section 3 | Roll Section 5 | Roll Section 6 | Roll Section 7 | Roll Section 8 | Totals |
| 210 Single Family Res. |  |  |  |  |  |  |  |
| 210-C Residential Condos |  |  |  |  |  |  |  |
| 220 Two Family Res. |  |  |  |  |  |  |  |
| 230 Three Family Res. |  |  |  |  |  |  |  |
| 240 Rural Res. with acreage |  |  |  |  |  |  |  |
| 241 Rural Res. (some ag. use) |  |  |  |  |  |  |  |
| 242 Rural Res. (recreation use) |  |  |  |  |  |  |  |
| 250 Estate |  |  |  |  |  |  |  |
| 260 Seasonal Res. |  |  |  |  |  |  |  |
| 270 Mobile Home |  |  |  |  |  |  |  |
| 271 Multiple Mobile Homes |  |  |  |  |  |  |  |
| 280 Multiple Res. |  |  |  |  |  |  |  |
| 281 Multiple Res. |  |  |  |  |  |  |  |
| 283 Res. w/Incidental Com. Use |  |  |  |  |  |  |  |
| TOTAL ASSESSMENT ROLL |  |  |  |  |  |  |  |

A breakdown of the number of properties with water frontage by residential property type will appear in Appendix B.

MUNICIPAL SUMMARIES – Property Type/Responsibility Grid			Table 1C   #1 OF ?

[For individual municipalities and all municipalities in total, e.g., a Consortium, and each individual municipality]

TOWN OF XXXX    SWIS - XXXX

20XX FINAL ASSESSMENT ROLL

| Responsibility: | M = Municipality | C = Contractor/Consultant |  |  | S = NYSDTF ORPTS |  |  | N/A = not applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Data Collection Method |  |  |  |  |  |  |  |
| Property Type |  | Initial | Re-collect | Verify | Valuation | Review | Assmt. Disclosure |  | Informals |
| Farm (100) | No. of Parcels |  |  |  |  |  |  |  |  |
|  | Responsibility |  |  |  |  |  |  |  |  |
| Vacant (300) | No. of Parcels |  |  |  |  |  |  |  |  |
|  | Responsibility |  |  |  |  |  |  |  |  |
| Residential (200) | No. of Parcels |  |  |  |  |  |  |  |  |
|  | Responsibility |  |  |  |  |  |  |  |  |
| Commercial (400) | No. of Parcels |  |  |  |  |  |  |  |  |
| Except condos | Responsibility |  |  |  |  |  |  |  |  |
| Commercial (400-c) | No. of Parcels |  |  |  |  |  |  |  |  |
| Comm condos | Responsibility |  |  |  |  |  |  |  |  |
| Commercial (400) | No. of Parcels |  |  |  |  |  |  |  |  |
| Complex | Responsibility |  |  |  |  |  |  |  |  |
| Industrial (700) | No. of Parcels |  |  |  |  |  |  |  |  |
|  | Responsibility |  |  |  |  |  |  |  |  |
| Utility | No. of Parcels |  |  |  |  |  |  |  |  |
| Advisories | Responsibility |  |  |  |  |  |  |  |  |
| Utility | No. of Parcels |  |  |  |  |  |  |  |  |
| No Advisories | Responsibility |  |  |  |  |  |  |  |  |
| Ceiling RR | No. of Parcels |  |  |  |  |  |  |  |  |
| (RS – 7) | Responsibility |  |  |  |  |  |  |  |  |
| Forest Land (900) | No. of Parcels |  |  |  |  |  |  |  |  |
| Private | Responsibility |  |  |  |  |  |  |  |  |
| Forest Land (900) | No. of Parcels |  |  |  |  |  |  |  |  |
| State-owned | Responsibility |  |  |  |  |  |  |  |  |
| Wholly Exempt | No. of Parcels |  |  |  |  |  |  |  |  |
| (RS – 8) | Responsibility |  |  |  |  |  |  |  |  |
| No. Parcels – Vendor/Consultant |  |  |  |  |  |  |  |  |  |
| No. Parcels – Municipality |  |  |  |  |  |  |  |  |  |
| No. Parcels – ORPTS |  |  |  |  |  |  |  |  |  |
| Total Parcels |  |  |  |  |  |  |  |  |  |

SECTION 3 - GENERAL RESPONSIBILITIES - MUNCIPALITY AND ORPTS

The successful completion of this project depends on the cooperation of several participants and their ability to successfully complete their assigned tasks as required by this RFP.  Following are the major responsibilities that must be performed by each.

[There should be a correlation between the physical and/or human resources a municipality can provide to this project and the savings to the proposed cost – the cost will almost certainly be higher if the municipality chooses to provide only oversight as opposed to differing levels of direct involvement.  The municipality may wish to add language to the RFP requiring prospective contractors to quantify savings for each direct component of municipal resources provided.]

3.1	Municipality

3.1.1  Project Management

The project administrator will have ultimate project responsibility.  The administrator will provide general direction throughout the project and timely resolution of problems when requested by any of the following:

- Contract Administrator (specify name and title);

- Contractor;

- Project Monitor (if hired); and

- ORPTS

The project administrator (specify name and title) will spend at a minimum   #   hours per week on this project.

[Does the municipality want the Assessor to act as project administrator?  The Assessor will sign the published reassessment roll and is directly responsible for the end results regardless of the actions of the contractor.  Will the Assessor have sufficient time to devote to this oversight role given normal day-to-day responsibilities?  Consideration should be given to hiring a Project Monitor if a reassessment hasn’t taken place in a long period of time.]

3.1.2  Data Manager

The municipality will provide a person to act as data manager who will work with the contractor, be trained by the contractor and / or ORPTS if applicable, and who will ultimately be responsible for file control and data management.  This person (specify name and title) will spend, at a minimum,   #   hours per week on this project.

3.1.3  Staff Involvement

The municipality will / will not provide appropriate staff, in addition to the Assessor or Assessor’s designee, to assist the project contractor, at the discretion of the project administrator throughout the duration of the project.   Staff will spend, at minimum, of   #   hours per week assisting on this project.

[Presumably this would be staff reporting to the Assessor.  Will Assessor’s staff have sufficient time to devote to direct involvement given normal day-to-day responsibilities?]

3.1.4  Documentation

The municipality will provide timely access to all current assessment roll, tax map, and jurisdictional information, i.e., but not limited to, RP-5217 forms, wetland maps, zoning maps, zoning ordinances, special district maps, and building permits.  The municipality will provide to the contractor within ten (10) days of project start up:

- One (1) electronic copy, e.g., PDF file, of the tax maps; and [posted on municipal website?]

- One (1) electronic copy, e.g., PDF file, of the assessment roll [see posting on municipal website]

Also, within ten (10) days of project start up, the contractor and the municipality will meet to determine the time frame and procedures for providing the contractor with:

- assessment roll changes;

- identification of new constructions and demolitions;

- building permits;

- sales documents (RP-5217); and

- other pertinent information.

At this meeting the contractor and the municipality will establish written procedures for allowing the contractor to have access to the inventory/assessment system and records.  [The municipality should consider whether it wants maintenance by the contractor to be made directly to its municipal file or to a work file housed on the contractor’s computer.  The municipality’s attorney should be consulted for implications relative to FOIL requests made while the project is underway.]

Prior to field review, the municipality and contractor must agree on documentation procedures for those parcels with significant changes in value, defined as a XX% variation between the computer generated estimate and the field reviewed value.  [Project administrator / Assessor will determine with contractor’s input which computer generated value will be used as the basis for comparison.]   In addition, the contractor shall provide a report by appropriate grouping (e.g., neighborhood, tax map section), in a mutually agreeable format listing (e.g., GIS map) the % change between the full value indicated on the latest final assessment roll and the preliminary value resulting from field review for all parcels.

3.1.5  Space and Equipment

The municipality / County Real Property Tax Services Agency will provide:

[Municipality should determine if the County’s RPTSA can provide space and / or equipment for this project.]

- #          square feet of office space located at:

______________________________________________________________________;

(ADDRESS)

- storage space;

- training areas;

- site(s) for informal reviews; and

- adequate furnishings;

at no charge to the contractor, for all required activities throughout the life of the project.    Access to this space is available between the hours of ____ and ____,    #   days a week.

The contractor may be responsible for providing its own telephone service including installation.  [This will ultimately be determined in contract negotiations.  The municipality may wish to have proposals submitted including this cost but specifying the amount to be deducted if this service is provided.]

[Discuss location of data processing equipment including printer.  Discuss access time to municipality's equipment.  Discuss whether contractor must provide own equipment; modems, printers, computers, etc.  Whatever space, resources, etc., the municipality can provide should help to lessen the cost of the project.  Municipality should encourage discussion with vendor to ensure compatibility of hardware, software, and other equipment used in conjunction with this project.]

3.1.6  Property Record Cards

The municipality is responsible for all expenses related to purchasing and printing bulk copies of the appropriate data collection forms (property record cards). [The municipality should consider if property record cards should be provided electronically for printing as needed.]

3.1.7  Assessor’s Participation

- The Assessor will be completely involved throughout this project.

- The Assessor will participate in all informational meetings and attend training sessions.

- The Assessor will provide the contractor with "local knowledge,” participate in data element selection and editing, field verification, value analysis, field review, and informal review meetings.

- The Assessor will review file maintenance corrections and the collection and verification of data related to new construction, building permits, and demolition.

- The Assessor will update all exemption amounts prior to assessment disclosure processing.

[Assessor should determine the responsibility of the valuation for parcels that are split between taxing districts.]

The Assessor will be available during the following project phases to assist the contractor as follows:

| PHASES | NUMBER OF HOURS PER WEEK |
| --- | --- |
| Project Start Up | As Needed |
| Data Collection | As Needed |
| Sales File Verification | As Needed |
| Valuation Testing / Production | As Needed |
| Field Review | As Needed |
| Informal Review Meetings | As Needed |

3.1.8  Clerical Function(s)

The municipality will perform the following clerical function(s) for the duration of the contract:  Insert Function(s).

3.1.9  Application for Advisory Appraisal

The municipality will / will not request advisory appraisals of taxable utility property and / or highly complex properties.  If applicable, the municipality must submit a request for advisory appraisals (forms RP-5050 and / or RP-7021) to the appropriate ORPTS’ regional office, nineteen months preceding the implementation of the reassessment (by October 1, 20XX).  A copy of Roll Section 6 must accompany the request (ORPTS’ delivery of advisories will be contingent upon the municipality’s participation in UCARS - Utility Company Assessment Roll Standardization).  In order to receive utility values, the assessing unit, its agents and ORPTS must agree to a schedule and the products to be provided.  Should the municipality file a plan for cyclical reassessment, utility advisories provided for the initial reassessment will be automatically be provided for subsequent years unless the municipality requests otherwise or the municipality does not maintain a Level of Assessment of 100% in the interim years.  Specific procedures for requesting advisory appraisals are found in Part 8195 of the Rules.

3.1.10  GIS Capacity and Availability

(Municipality to Describe, including available layers)

[The municipality is strongly advised to make its GIS capacity available to the contractor and expect ten (10) maps at a minimum including the following, as applicable, to be delivered at mutually agreeable times throughout the project]:

- Residential Sales (excluding condominiums unless Homestead is in place or will be considered)

- Commercial Sales

- Commercial Parcels with Income & Expense Filers Highlighted

- Informal Review Parcels

- Inspected Parcels

- Parcels with a taxpayer inquiry

- Land Value Per Square Foot

- Improvement Value Per Square Foot

3.1.11  Software, if other than RPS.

(Municipality to describe software requirements here)

[Example: The computerized assessment roll system utilized by the municipality is run by the XYZ Assessment Administration System and/or XYZ CAMA System which, upon conversion, shall be compatible with RPS.  Also, because the municipality utilizes XYZ sketch software package, it shall be used by the Contractor for all building sketches.  In all instances, conversion/transfer of data of XYZ(s) to RPS and vice versa shall be the responsibility of the Contractor.  At this time, it is the intention of the municipality to maintain the computerized assessment roll in the XYZ software(s).]

For quality control purposes and to help ensure ORPTS is able to verify the reassessment roll at the municipality’s stated Level of Assessment, the contractor  must be able to provide the municipality with a complete file (all assessment, inventory, sales and sales inventory) in an RPS compatible format at appropriate stages of the project (e.g., during data collection, after all applicable sales data has been reviewed, at the onset of mass appraisal activities, at the end of field review prior to the start of assessment disclosure processing and prior to the publication of the tentative roll).

3.1.12  Payments to Contractors

Payments shall be made promptly in accordance with Section 8 of this RFP.

3.2	ORPTS

3.2.1  Software

If RPS is used, ORPTS will provide assistance with use of this software.

3.2.2  Data Collection Material

ORPTS provides:

- data collection manuals (for a fee); or available on DTF website at: http://www.tax.ny.gov/research/property/assess/manuals/assersmanual.htm

3.2.3 Processing Fees

Computer processing fees are billed to the municipality and will be based on the Real Property System Fee Schedule for the fiscal year in which the processing actually occurs.  For projects that extend over multiple fiscal years, the most current fee schedule should be referred to when preparing budgets and expenditure plans.

3.2.4  Advisory Appraisals

Upon receipt of a request for advisory appraisals and a copy of Roll Section 6, ORPTS will review existing resources and number of requests.  ORPTS will advise the municipality by July 1st preceding the implementation of the reassessment if it is able or unable to provide advisory appraisals.

The contractor will be responsible for any valuation for which ORPTS’ advisory appraisals are no available or not provided.

3.2.5  General

ORPTS will assign regional staff who will be responsible for monitoring project progress, consulting with the municipality and others and providing advice and assistance as needed.  ORPTS will participate in public relations activities with the contractor and local officials upon request and adequate advance notice.

ORPTS will provide upon request:

- Statewide information which would include sales data through Sales Web, municipal profiles through MuniPro, statewide assessment data through Parcel Database and GIS data;

- Statewide generic valuation factor file;

Any charges applicable from the current fee schedule as established by the SBRPTS will apply.  All charges will be billed to the municipality.

SECTION 4 - PROJECT REQUIREMENTS/CONTRACTOR RESPONSIBILITIES

4.1	Project Management

The contractor is responsible for providing professional personnel capable of successfully accomplishing the responsibilities as defined in this RFP.  Minimum staffing requirements are found in Section 6 of this RFP.

[The municipality should give due consideration to both the staffing requirements and the degree of experience and/or licensure desired of that staff relative to the work that must be performed for a successful completion of this project.]

The contractor is responsible for performing all project related clerical function(s) not specified as a municipal responsibility.

4.2	Project Timetable

On the following pages is the proposed timetable for this project.  If the company deems it necessary to alter this schedule, the company must specify any changes in its proposal.  If changes are made, please so note in Appendix D sample proposal in response to request for proposal.

| RFP SECTION | PROJECT TIMETABLE [Public Relations Plan should be integrated in this timetable. Suggestions below are for general guidance but may not be appropriate for the specific project being considered. ] | START DATE | FINISH DATE |
| --- | --- | --- | --- |
| 4.2 | Project Timetable [begin at contract signing / end with Final Assessment Roll] |  |  |
| 4.3 | Public Information Program [begin at contract signing/ end with Tentative Assessment Roll] |  |  |
| 4.8.11 | Photography/Image Option [begin with Data Collection / end with completion of new construction] |  |  |
| 4.4.1 | Data Collection Training [typically, one month] |  |  |
| 4.82 | Pre Inspection Data Entry (Based on existing, ideally, already scanned Property Record Cards) [does municipality want existing data used as starting point for this project?] |  |  |
| 4.4 | Local Staff Has Been Fully Trained In all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #1 |  |  |
| 4.8 | Subject Inventory Data Collection [determine number of inspections per month per data collector to develop time frame] |  |  |
| 4.8.4 | Subject File Creation / Modification [begin one week after start of data verification/collection / end 1-2 weeks after verification/collection finishes] |  |  |
| 4.9 | Sales Validation, Verification and File Creation [begin at start of data collection / end four (4) months after Valuation Date or through tentative roll.] |  |  |
| 4.8.5 | Collection of New Construction (Clean-Up Data Collection) [if contractor is responsible for collecting new construction] |  |  |
| 4.4 | Local Staff Has Been Fully Trained in all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #2 |  |  |
| 4.8.10 | Post Inspection Parcel Inventory (Data Mailer or Web Site Alternative) [begin one month after start of Data Collection / end one month after completion of Data Collection] |  |  |
| 4.8.10 | Production in Response to Parcel Inventory Mailers [begin with Data Collection / end with completion of follow up on informal reviews.] |  |  |
| 4.10 | Valuation Editing [begin with Sales File Creation / end one week prior to Field Review] |  |  |
| 4.8.10 | Acquisition of Market Data (Income & Expense questionnaires) |  |  |
| 4.11 | Grouping of Data (neighborhood analysis/delineation) |  |  |
| 4.11 | Valuation Testing [From Creation of Sales File Until One Week Prior to Field Review] |  |  |
| 4.4 | Local Staff Has Been Fully Trained in all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #3 |  |  |
| 4.11.4 | Valuation Production [the week prior to beginning Field Review] |  |  |
| 4.12 | Field Review of Values [determine number of parcels per day per field reviewer to determine time frame / complete two months prior to start of Assessment Disclosure Processing] |  |  |
| 4.13 | Assessor’s Value Review with Contractor [determine number of parcels per day to be reviewed to determine time frame / complete one month prior to start of Assessment Disclosure Processing] |  |  |
| 4.4 | Local Staff Has Been Fully Trained in all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #4 |  |  |
| 4.13 | Update Values on File [ongoing / complete three weeks prior to beginning Assessment Disclosure Processing] |  |  |
| 3.1.7 | Assessor’s Recalculations of Exemptions [complete one week prior to Disclosure Processing] |  |  |
| 4.14 | File with preliminary assessment, inventory and sales data ready for Assessment Disclosure Processing [minimum 3.5 months prior to Tentative Roll filing date) |  |  |
| 4.14 | Assessment Disclosure Notice Production and Analysis [complete at least one week prior to Assessment Disclosure Notice mailing; at least three weeks earlier if Homestead Tax Option is being considered] |  |  |
| 4.4 | Local Staff Has Been Fully Trained in all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #5 |  |  |
| 4.14 | Assessment Disclosure Notice Mailing [minimum three months prior to Tentative Roll filing date] |  |  |
| 4.15 | Informal Review Meetings (including Field Related Activities) (begin one week after Disclosure Notice Mailing and complete one month before Tentative Roll filing date) |  |  |
| 4.16 | Value Change Notices Production [three weeks before Tentative Roll filing date] |  |  |
|  | Prepare Tentative Assessment Roll and file [Tentative Roll filing date] |  |  |
| 7.0 | Project Deliverables to Assessors [no later than Tentative Roll date] |  |  |
| 4.19 | Submit Application for Appropriate State Aid Reimbursement [two weeks prior to State deadline] |  |  |
| 4.4 | Local Staff Has Been Fully Trained in all phases of the project completed to date. |  |  |
| Appendix E | Assessor’s Sign Off Document #6 |  |  |
|  | Project Completion [Final Roll Publication Date] |  |  |

4.3	Public Information

[This is a critical factor in a successful revaluation and should be a high priority!]

The contractor must conduct a comprehensive public information program designed to coordinate all activities necessary to promote public understanding, awareness, and cooperation throughout the project.  The contractor must be prepared to conduct a public information campaign that will include media releases, direct mailings to all property owners, programs for broadcast and rebroadcast on television and radio, the internet and oral presentations.  Individual presentations will be directed to property owners, local officials, businesses, and civic groups so that they may better understand the scope and objectives of the project.

[MUNICIPALITY SHOULD DESIGN PUBLIC RELATIONS PROGRAM AND INSERT in Appendix G.]

[The understanding by the public of the goals of the reassessment and the processes used cannot be overstated as a means to help ensure a successful implementation.  To this end, the municipality should give careful thought to the public relations challenges that may exist in the municipality and how those best can be addressed (e.g., are there certain neighborhoods that are likely to see a larger increase in values than others (those areas that are generally under assessed)? Are there certain groups that may be concerned about the effects of reassessment?  Are there active property owner groups in the municipality that should be addressed? Also, FAQs, Online Property Information, Photography, & Videos should be strongly considered. Workshops with a limit of participants not to exceed what the instructor(s) can handle may be preferable to public meetings with unlimited numbers of people attending.  All public relations materials should be approved by the municipality prior to use.]

At a minimum, this program should include the time frames and method (meetings, mailers, media, etc.).  If appropriate, the municipality should mention the need for any bilingual public information material.  Public information releases associated with the following phases of the project should be included, at a minimum:

- contract signing

- public information meeting schedule

- general project information

- data collection

- inventory mailer

- assessment disclosure / informal review

- project status updates

The contractor will conduct the prescribed meetings at various locations throughout the municipality. The contractor should be prepared to conduct up to            public information sessions/workshops.

All public information activities should strive to emphasize the responsibilities of the various participants, the methods to be employed during the project and the overall goals.  At a minimum, the following points should be addressed as often as possible:

- significance of real property tax;

- necessity of project;

- purpose and methods of project;

- documented methodology and criteria for the values established;

- role of municipality and Assessor(s);

- role of project contractor;

- role of ORPTS;

- necessity of data collection;

- caliber and training of data collectors;

- cooperation of parcel owners (public/private partnership) is key to success;

- assessment disclosure aspect throughout the project;

- ongoing nature of system; and

- property valuation versus taxation.

The contractor will provide in its proposal a detailed outline and schedule, by project phase, of the intended public relations endeavors.

The contractor should include in its proposal sample press releases and brochures/pamphlets used in previous projects conducted by the firm.  If the company is selected, these materials may be used to develop a comprehensive public information campaign for this project.

4.4	Local Staff Training

The contractor is responsible for training local staff in such a manner that, at the end of the project, appropriate municipal staff will be knowledgeable in the operation of those phases of mass appraisal assigned as a contractor responsibility.  The contractor is also responsible for training personnel under its control in order to maximize their usefulness.

[Ideally, it is important for the municipality to ensure that its Assessor and assessment staff will be in a position to assume the maintenance of inventory and values at the same stated Level of Assessment as will be implemented in this project.]

The contractor is responsible for conducting a thorough, effective, and documented training program for:

- data collectors;

- municipal staff including the Data Manager;

- the Assessor; and

- Board of Assessment Review members [ensuring attendance of BoAR members at any training is the responsibility of the municipality]

The minimum standards for conducting training will include the following:

Lesson Plan – Outlines and lesson plans for training for all aspects of the project which shall describe the material to be presented and the techniques to be used.

Training Manual – A comprehensive reference tool depicting the substance of the lessons to be given with, at least, definitions, applicable illustrations, explanations of computer assessment administration concepts and necessary flow charts.

Schedule of Training Sessions – A detailed outline which specifies dates, sites and content of each class necessary to be conducted within the framework of this project.  [The municipality should develop target dates and a training schedule.]

This information will be provided to the project administrator for approval prior to any training session taking place.

In its proposal, the company will provide a general training schedule that it intends to follow during the project.  However, within fifteen (15) working days of contract execution, the selected contractor will provide a training plan for data collectors.  Also, within twenty (20) working days of approval of a contractor work plan, the contractor will provide a detailed training plan and schedule for the remainder of the training responsibilities.  Municipal personnel must be permitted to participate fully in all training activities.

4.4.1  Data Collector Training

Training for data collectors must be comprehensive and documented.  The data collection training lesson plan and manual (Assessor’s Manual volume 6), as prepared by ORPTS, will be used for this training.  Training sessions must be conducted in both a field and classroom environment.  Attendance logs must be maintained for all classroom sessions.

ORPTS’ staff will NOT provide or conduct data collection training for any contractor staff unless the municipality and ORPTS’ Regional Management agree to this AND it is clearly specified in this project RFP, in advance.  Without such specification, contractor staff are welcome to attend a previously scheduled training session if there are available seats.

4.4.2  Training of Municipality Staff & Local Assessor

The contractor is responsible for training municipal staff and the Assessor(s) so that they can routinely interface with assessment administration modules as they relate to the company's involvement and be familiar with the basic concepts of valuation by the end of the project.  Formal training will include, but is not limited to, such topics as:

- data collection;

- valuation;

- field review;

- RPS file maintenance procedures;

- file control concepts of the system; and

- income and expense data analysis necessary to maintain a current "valuation factor file"

[In addition to training requirements as defined as the result of completed needs analysis]

The contractor must provide municipal staff the following workshops:

| WORKSHOPS | MINIMUM LENGTH OF WORKSHOP | DATES |
| --- | --- | --- |
| Land Analysis / Valuation |  |  |
| Cost Analysis / Valuation |  |  |
| RFV Market Analysis / Valuation |  |  |
| Commercial Market and Income Analysis / Valuation |  |  |
| Field Review |  |  |
| Subsequent Roll Value Maintenance |  |  |
| Board of Assessment Review | 4 Hours |  |

In addition, the contractor will provide on-the-job training in the practical application of file maintenance for the municipality's data manager and Assessors. This will enable them to become aware of the practical application of assessment administration.

The contractor will provide the Assessor (insert number of days) of on-the-job field review training, after completion of the field review workshop specified above. Within two weeks of the start of field review, the contractor must have individualized follow-up training for Assessor’s staff.  During the field review phase of the project, the contractor must allocate time in conjunction with the project status meetings to answer individual field review questions.

[The municipality should note the degree to which the Assessor and his/her staff can participate in field review with the contractor’s staff is the degree to which valuation issues can be identified and adjusted prior to the mailing of preliminary assessments as part of assessment disclosure.]

The contractor may offer additional training or workshops as part of its proposal on a per diem basis.

4.4.3  Board of Assessment Review Training

The contractor is responsible for providing the Board of Assessment Review with:

- an overview of the reassessment project;

- the basics of mass appraisal;

- familiarization with the valuation concepts used;

- field review procedures; and

- valuation/field review reports

- familiarization with the USPAP compliant reassessment documentation for this project

This training will be conducted in a classroom environment and consist of a minimum of four hours and the County’s Real Property Tax Director shall be provided the opportunity to attend.  The contractor shall not be held liable in any way if Board of Assessment Review members choose not to attend.

4.5	Data Processing

Data Manager [Alternative if municipality doesn’t want to provide a data manager]

The contractor will provide a person to act as data manager, who will evaluate in conjunction with the municipality’s Information Technology Director, the adequacy of the municipality’s existing hardware and software used for assessment purposes and make a recommendation, if appropriate, relative to needed upgrades. Ultimately, the contractor will be responsible for file control and data management.  The contractor’s data manager will be responsible for training the assessor and assessor’s staff in file control and data management.  [Delete this section if not chosen by municipality.]

4.5.1  Hardware

The valuation phase will be carried out using the municipality’s computer(s) on site or on the contractor’s hardware with no charge for computer usage to the contractor.  All costs for outside valuation processing, if applicable, are to be paid by the municipality/contractor.

[The pros and cons of data being maintained on the contractor’s hardware vs. the municipality’s hardware should be discussed.  See guidance language for section 3.1.4.]

4.5.2  Software

NYS DTF - ORPTS’ computer programs may not be modified without permission of NYS DTF.  New programs will not be written and existing non-NYSRPS programs will not be used for this project without the permission of the project administrator.  Existing contractor software developed for personnel and financial management of the project shall not be subject to this provision.

For quality control purposes and to help ensure that ORPTS is able to verify the reassessment roll at the municipality’s stated Level of Assessment, the contractor  must be able to provide the municipality with a complete file (all assessment, inventory, sales and sales inventory) in a RPS compatible format at appropriate stages of the project (e.g., during data collection, after all applicable sales data has been reviewed, at the onset of mass appraisal activities, at the end of field review prior to the start of assessment disclosure processing and prior to the publication of the tentative roll).

4.5.3  Scheduling

If printing is to occur at an ORPTS’ regional office, the contractor will submit to ORPTS, for approval, weekly forecasts of anticipated computer usage, one week in advance, to ensure printing time.

4.6	Tax Map Data

[Detail the Status of Tax Maps]

Tax map errors may be discovered during the data collection effort.  These errors are to be reported to the project administrator by the data collectors as they are discovered.  The project administrator will furnish the contractor with tax map inventory changes, in report form, as determined in Section 3.1 of this RFP.  In its proposal, the company must explain how errors in tax maps found in the field will be recorded.  All instances must be reported to the project administrator within five days of discovery.

4.7	Property owner Inquiry

Contractor personnel, familiar with the entire project, must be dedicated to the function of resolving property owner inquiry and complaint follow-up.  All property owner inquiries and complaints must be fully documented and must receive a response.

At a minimum, the following will be forwarded to the municipality’s designated contact person:

- name of inquirer or complainant;

- time and date of inquiry/complaint;

- nature and specifics of the complaint, including the applicable property address;  and,

- the response to the inquiry or complaint

[The municipality should determine the time frame for receiving this documentation, i.e., weekly? monthly? within X days of occurrence?]

There may be instances where certain inquiries, complaints and/or questions will be of such a nature that they will require intensive research and analysis by the vendor.  Before the vendor dedicates any time or resources to these extraordinary instances, they must be brought to the attention of the municipality for a determination of the manner, scope and time necessary for such a response.  The municipality will determine whether a response will be made and under what circumstances.

4.8	Subject Inventory Data Collection

4.8.1  Verification and Collection

[Extremely important: Where a county-wide sales file or sales from outside the municipality may be used for valuation, the Assessor, to the degree possible,  should make sure data is collected uniformly with the rest of the municipalities in the county so the Assessor and contractor can be confident in the use of neighboring municipalities’ sales inventory.]

All data collection is to be conducted in accordance with Volume 6 of the Assessor’s Manual published by ORPTS.

The contractor will conduct an on-site inspection as defined by the Rules and the Guidelines for Cyclical Reassessment of all parcels to be valued within the scope of this project.

[The property inventory collected will play a tremendous role in the accuracy and consistency of the assessments developed and, consequently, the public's perception of the project's quality and fairness. The municipality must consider how it wants data collected.  Is data to be collected as a complete data collection without referring to existing property record cards (complete inspection / measurement)?  Will it be a verification of existing data in which properties are viewed from the public right-of-way with on-site inspection and / or measurement as needed in the event discrepancies are noted?  Will the municipality use oblique aerial photography and / or 360 degree street level photography as a resource to obtain data and identify specific properties requiring recollection in advance of field inspections?  Does the municipality want interior inspections of homes attempted?  Does the municipality want different levels of data collection (e.g., data verification for residential, data collection for commercials)?  Data collection options must be weighed very carefully as each will have implications for the potential cost of the project as well as the public's perception of the quality of the project's results.  The data collection options desired by the municipality should be reflected in the language used in the pre-inspection mailer (see section 4.8.2).

Developing a data collection program that balances any potential public sensitivity to perceptions about the invasiveness of data collection with the need to obtain accurate inventory will help to minimize negative public reaction during the project.  When a project will include data collection that requires contractor staff to set foot on private property, due consideration should be given to ORPTS Opinion of Counsel volume 9 number 4 .  This Opinion of Counsel should be shared with the municipality's attorney and discussion should occur between the attorney, assessor, municipal executive and municipal board to ensure consensus on the appropriateness of any data collection approach prior to the issuance of this RFP.]

The collection of parcels is to be conducted by a data collection crew to be hired and trained by the contractor [This statement may require rewriting based on decisions made by the municipality – see comments under Section 3 Municipal Responsibilities, p. 17.]

4.8.2  Collection Instrument

The standard ORPTS’ property record card will be used in this project; RP-3100 for residential, farm and vacant, and RP-3105 for commercial, industrial and public utility parcels.  [Does the municipality want to consider the use of a hand held data collection device? Please note that reassessments are an opportunity for the introduction of new technology. Regardless of data collection format, are there additional property characteristics beyond the standard choices that need collection for a more accurate property valuation?]

Property description data in the project will be of two types:  "front-loaded" data and field collected data.  The "front-loaded" data currently exists for each parcel, in machine-readable form, and must be placed on the data collection card prior to data collection.  This data will be resident at the parcel level in the RPS format.  This data includes, at least, the following items:

- parcel ID (parcel key);

- owner name;

- owner address;

- parcel location;

- property class code; and

- parcel size

A notice detailing the purpose of the data collection project is sent to each property owner at least one week prior to the commencement of data collection activities.  This notice shall detail the general procedures to be used in the data collection effort and specifically outline the procedures that will be followed if no one is at home during the first entry attempt.  A procedure for property owners to proactively refuse all access to their property must be included.  (Insert procedure developed for municipality via appendix.) [Building Permit issues should be discussed. While not necessarily pertinent to the services the prospective contractor will offer, does the municipality wish to consider some sort of amnesty program for improvements already in place that were made without appropriate building permits / certificates of occupancy?]

4.8.3  Parcel Entry

The contractor will attempt to perform a complete interior inspection of all improved properties.  The data collectors are required to indicate whether entry was made.  Where entry is made, the contractor will attempt to secure the signature of an owner or adult occupant. (If no one is at home the data collector must leave notification of the visit or must notify owner by mail within ten (10) days.)  The Property Description Report / Data Mailer cannot be used for this notification.  Instructions on how the occupant may set up an appointment for an inspection are to be supplied.

In the case of total refusals, signatures should be obtained and a list of all such refusals will be given to the project administrator for assistance in gaining entry.

At least two (2) entry attempts (initial attempt and one callback) are required in all cases where entry, except for outright-signed refusals, has not been made.  The second attempt must be made either in the evening (after 6:00 pm) or on weekends. The contractor must be sensitive to and take note of the observance of religious holidays and the Sabbath.

After two (2) unsuccessful entry attempts have been made, the contractor must forward a notice to the parcel owner, of attempted entry that details a procedure whereby the owner may schedule an interior inspection with the contractor.  The Property Description Report / Data Mailer will suffice as this notice.

A list of those parcels for which there was no affirmative response must be given to the project administrator for a final entry attempt.

Where there are gated properties or homes that cannot be accessed or viewed from the public right of way, it may be necessary to schedule appointments to gain entry.  Because these properties, among others, may require substantially more time to measure and gather data, the contractor, therefore, must plan for sufficient time for on-site inspection.

The contractor will maintain a summary record in a mutually agreeable format for each property detailing what was done for each inspection or denial of entry.

4.8.4	File Creation and Maintenance

Inventory data records are to be created and or corrected within ten (10) working days after the last required visit to the property or refusal.  Documents for parcels that are data collected are to be manually verified for completeness and computerized.

All property data collected must be entered into the computer on-site at the contractor’s office or municipal office as determined and be available for internal quality control and review by _________.  [Municipality should determine the time frame in which data entry must occur relative to completed inspections.]

The contractor will be responsible for all data security during the course of the project.

The contractor is responsible for the data collection of all parcel changes that are reported to the contractor prior to taxable status date of the implementation year.  Examples are changes due to:

- parcel splits;

- parcel merges;

- demolition;

- fire; and

- new construction

The project administrator is responsible for the reporting of such changes to the contractor as agreed upon in Section 3.1 of this RFP.

All parcels will be edited and file maintained prior to Property Description Report / Data Mailer production.  At that time, a complete set of edit reports is to be given to the municipality and ORPTS.

Property Description Report / Data Mailer discrepancies must be resolved and corrections made to the inventory file prior to valuation testing.

Throughout the project, the contractor will make available, upon request, all edit reports and subsequent output reports to the project administrator and ORPTS.

4.8.5  Parcel Improvement Sketches

[Is the municipality currently using sketch software and should this software be used for this project?  How are sketches to be stored?]

Sketches for all improved parcels will be done in a manner prescribed in the NYSDTF - ORPTS’ Assessors Manual Volume 6 Data Collection.

The contractor will sketch all buildings and physical improvements to scale on the predetermined form/format.  Sketches will be drawn to the nearest half foot and all sides labeled, using the labeling procedures outlined in Volume 6 of the NYSDTF – ORPTS’ Data Collection Manual.  Sketches must be produced for each condominium unit as well.  When available, master deeds and associated floor plans can be used as the basis for producing sketches.  There are no exceptions to the inspection requirements for condominiums.

The Contractor will be responsible for vectoring the field sketches into a digital sketch format.

The computerized sketches shall conform to the most updated standards and clearly show all dimensions and story heights for primary and secondary structures.  The corresponding defined areas of each floor and/or structure will also be calculated for and show square footage of living/building area.

[NOTE: For municipalities that have not conducted a reassessment within the last six (6) years, the municipality should consider a separate contract in which property record card sketches and/or digital sketches are compared to the latest available ortho-photography, ideally oblique aerial photography, if available, so a report can be provided to each applicable Assessor identifying differences of square footage greater than 10%.]

A plot plan must be submitted for those complex parcels as listed in Appendix B.

4.8.6  Data Collectors

The minimum number of data collectors and crew chiefs to be employed for the project shall be sufficient to collect the required data items within the time scheduled.  Crew chiefs are primarily responsible for the recollection and / or field verification of data collected by the data collectors.  The crew chief's functions include monitoring and ensuring the quality, consistency and accuracy of all data. A ratio of not less than one crew chief for every five data collectors must be maintained.

[The municipality / contractor may propose use of a handheld (on-site) data entry device.]

[It is imperative that data collectors are appropriately qualified and also sensitive to the concerns of the homeowners in regard to data collection procedures. The municipality shall specify the level of qualifications and credentials of data collectors employed for this project.  The contractor shall ensure that all data collectors have been engaged in similar employment in at least two municipal-wide reassessments, previously. Preparers of this RFP should ensure that required background of data collectors as stated in the glossary is repeated here.]

4.8.7  Data Quality Control

Each crew chief will be required to field verify twenty-five (25) of the first one hundred (100) residential parcels and twenty-five (25) of the first one hundred (100) parcels in the farm, commercial and industrial categories that have been collected by each data collector within 30 days from the start of data collection for each collector.  [Does the Assessor / project administrator wish to offer any parameters under which a waiver for this requirement would be granted to applicable data collectors?]  The documented results of this verification of data must be reported to the project administrator and ORPTS’ liaison and the reason for any differences must be determined immediately.

In all cases where an individual or group of data collectors is collecting data erroneously, due to lack of skills, the collector(s) must be recalled for intensified retraining or termination.  The work of those collectors who have been retrained must be field verified at a frequency of one (1) out of every five (5) parcels for the next fifty (50) parcels.  Continued failure to collect data properly after retraining will constitute cause for dismissal of the data collector.  In all cases where the reason for collection differences is based on the failure of a collector to carry out his/her duties, that collector will be promptly terminated.

Upon return from the field, each data collection instrument is to be visually checked by contractor office staff for completeness and legibility.  Insofar as possible, that check and any follow-up clarification will be gained from the data collector on the day following the return of the card from the field.  In addition, Property Description Reports (also known as Data Mailers) as described below will be an integral part of the quality control.  The quality control must include a procedure for remedying any failures or discrepancies in the accuracy of the data as revealed by the field verification of data, or brought to the attention of the contractor by other knowledgeable persons.

The company will include in its proposal, a detailed quality control program.  In addition to the previously mentioned criteria, the program must include a comprehensive weekly reporting procedure to the municipality that details collection staff, each collector's work, municipal level progress summaries and estimates for the upcoming week.

4.8.8  Vacant and Agricultural Land

All vacant and agricultural lands are to be listed on the appropriate property record card with appropriate land breakdown(s).  For parcels in an agricultural district, or for parcels currently receiving an agricultural exemption, land breakdowns are to be noted separately for eligible and ineligible lands as categorized on the exemption application.  This may require multiple entries of some land types.

[While not necessarily a part of this RFP, the Assessor should be prepared to guide contractor staff in how land breakdowns are to be delineated (e.g., based on minimum zoning requirements for development? Using a base lot size?).  The Assessor should be prepared to note both positive and negative value influences to land that should be collected as part of this project (e.g., the collection of water frontage data for applicable parcels, the use of vacant primary vs. vacant undeveloped land types, the use of front footage vs. acreage, etc.).  A discussion of this nature is likely to occur at pre-proposal meetings and /or company interviews.]

4.8.9  Public Utility Parcels and Ceiling Railroad Parcels

The contractor shall collect the land data items using form RP-3105 for parcels in the public utility category, if the assessing unit indicates that the full value produced by the advisory appraisals of public utility property provided by NYSDTF-ORPTS will be used in the reassessment.  If such advisory appraisals will not be used, a set of data items must be collected and recorded that are necessary and material to estimate the full value of the public utility parcels, including a detailed inventory of all improvements classified as real property for which a replacement cost less depreciation can be estimated.

The contractor shall collect the land data items and all structural properties using form RP-3105 for ceiling railroad parcels.  Non-structural property, including trackage, shall be collected according to the procedure described for the valuation of unique and highly complex parcels.

4.8.10  Property Description Report (also known as Data Mailer)

[Data mailers are not a requirement to qualify for State aid.  Many municipalities view data mailers as a public relations tool that is part of the reassessment project.  Data mailers are also viewed as another attempt to verify property data.  The municipality should determine if the results merit the cost, e.g., does the municipality want to place this data online to save on postage, increase transparency, and, potentially, reduce the number of inquiries?  Additional considerations include: What property classes, i.e., residential, farm, vacant land, and / or commercial, would receive data mailers?   Does the municipality want to send data mailers in advance of any data collection effort?]

Property owners will also play an important role in monitoring the quality of data collection.  Upon completion of the process (defined as a parcel which has been data collected in the field, manually verified for completeness, entered onto the inventory file, computer file edited and all corresponding errors corrected), data mailers can be sent to owners of each parcel of property in the residential, farm, and vacant categories.  The mailers, which will consist of a selected property description as collected by the contractor, must be sent in sufficient time to allow for resolution of inquiries prior to use.  A cover letter that explains the purpose and content of the mailer, and the procedure whereby the property owner may schedule an appointment for collection should be included with the mailer.  An explanation of the fields to be displayed on the mailer as well as the potential entries for each field should accompany the mailer and cover letter.   Production of these notices, as well as folding and envelope stuffing, if required, will be a contractor responsibility. [Ensure this is consistent with statement of mailing / stuffing / postage responsibility as it appears in RFP section 3.1.8.]

Upon completion of data collection of the parcels in each of the other property classification categories within the municipality, a notification, by mail, will be sent to each of these parcel owners that the data items collected may be reviewed at a stated time and place within the municipality.  Commercial data mailers available in the RPS system may be substituted for this notification requirement. Again, the mailers must be sent in sufficient time to allow for resolution of inquiries prior to use.

Property owners will be asked to review the property inventory data descriptions and report any discrepancies.  [The municipality should determine return policy for mailers, e.g., should all mailers be returned regardless of the presence of discrepancies?] Mailer returns will be sent to the contractor for analysis. The contractor will resolve all data problems as indicated by property owners' responses prior to commencement of valuation activities.  Telephone inquiries as a result of data mailers are the responsibility of the contractor.

The contractor will mail a questionnaire to owners of commercial/industrial property, prior to or concurrent with the inventory mailing, which will request all appropriate income and expense information.  [Does the municipality want to consider an Income & Expense application that could be submitted securely on-line?]

4.8.11  Photography/Image

The photography aspect of the project is seen as an opportunity to enhance the quality of data, supply an additional tool for the review of values and to increase the public's confidence in the project.  To help attain these goals, the following guidelines have been prepared.

To ensure the quality of the images:  Each image is to be identified by the appropriate section, block and lot number.  Each image shall be sharp and the dimensional sides of the structure clearly defined.  Where possible, the structure captured must fill at least fifty (50%) percent of the horizontal frame.  No more than one structure shall be contained in each image except in those cases where an attached or semi-attached garage is present.  Wherever possible, the image must depict the front and side view of the structure (the length and width).  The structure should not be obstructed.  [Does the municipality want photographs taken of vacant lands?]

The contractor shall provide to the project administrator, in batches, [the municipality should specify size and frequency of batches] the images (photos, video) for review.  The project administrator must review and accept or reject the images within 30 days of receipt.  The project administrator will review the images for quality, sharpness, accuracy, and that the structure is clearly defined.

There must be an accurate link between the image and the parcel.  Therefore, the company, in its proposal, shall include:  A description of the equipment to be used and discuss the method of identification used to ensure the link of images to corresponding parcels shall be mutually agreeable.  The initial parcel imaging shall be completed before field review, in order to provide the municipality / contractor the opportunity to review the image and linkage to the parcels.  The images shall be used as an additional quality control measure during the field review process.

The company shall, in its proposal, outline the procedures to be carried out for the security and backup of all images.  The company must provide a detailed list of all equipment and associated cost, i.e., hardware, software, imaging devices, which will be utilized at the municipal level for viewing, printing images, and updating.  The company shall provide an outline of the training program for municipal staff in the implementation and operation of the image system as well as a description of the procedures and the associated cost with updating the image file.  The company must describe its procedures for linking the image file to an assessment file.  All copyright and ownership rights to the completed image file must be fully and explicitly disclosed.

[While the language in this RFP is geared towards more traditional individual images, whether digital or 35mm, does the municipality want to have oblique aerial and/or 360 degree street level photography as an alternative or option?  If so, language should be added stating whether the responsibility for contracting for 360 degree street level photography and/or oblique aerial photography will be a contractor or municipal responsibility.  Additionally, if chosen, the intended timeframe for completion of this photography should be stated as well as the municipality’s expectations for how the contractor will or will not use these images in conjunction with this project. The municipality should state the circumstances under which the contractor is expected to take new images if imagery exists.]

4.9	Sales Inventory Collection and File Creation

The contractor is required to collect and verify the data for those parcels located throughout the municipality that have sold since determine DATE and for all sales occurring through the project’s valuation date / taxable status date.  [The municipality will determine in consultation with the contractor, the municipalities and / or school district segments from which sales outside of the municipality will be collected, if needed.]

For parcels where inventory as of date of sale differs from subject inventory, a separate inventory for the sale parcel must be completed.  There must always be a subject and sale record.

4.10	Data Edits

The contractor will submit to the project administrator and ORPTS a list of the proposed edits prior to file editing.  ORPTS will advise the project administrator as to the applicability of these edits and the final edits will be mutually agreed upon by the contractor, the municipality, and ORPTS.  These edits will remain frozen until a change becomes necessary and has been agreed upon by the three parties.  The contractor will be responsible for resolving all errors that result from the edit runs.  It is the contractor's responsibility to provide a complete inventory file for valuation that is as error free as possible.  This inventory file must be available to the municipality prior to valuation.  In the event that the data inventory file shows unacceptable levels of inventory discrepancies, ORPTS reserves the right to withdraw support for this project.

The contractor will submit to the municipality a copy of the output reports from the valuation edit program.  The contractor will resubmit to the municipality a copy of the error reports from the final run of the land, cost and commercial edit programs prior to valuation.

[A standard set of edits is available in RPS.]

4.11	Valuation

Computer-generated values, to be reviewed in the field, will be produced by the contractor, for all properties, as defined in the RFP, utilizing Mass Appraisal techniques.

The contractor must provide the municipality with an overview of the general valuation methods used on this project for use by local officials.  In-depth documentation for use by Assessor’s staff will also be provided.  This will include a written summary of the land methodology used for each neighborhood, a depreciation schedule for all improvements (so that buildings can be costed in the field, if necessary) and time trend documentation, market coefficients and comparable selection points.

4.11.1  Residential/Farm/Vacant

The market value and cost approaches will be the primary methods of valuation for these properties. Computer-assisted valuation for residential, farm, and vacant parcels will take place after all edits on the subject and sales inventory files are addressed.  This function can be separated into three phases.

The first phase of the valuation process is the valuation of land.  This phase requires extensive analysis of the sales base as well as input from the Assessor(s).  The contractor, with assistance from the Assessor(s), determines unit land values for all types of land within the municipality.  The contractor enters these into the land tables of the land value extension programs.  Values must be computed for each separate land use classification associated with each parcel.

The second phase of the valuation process employs the cost approach.  The contractor utilizes the sales base to determine market adjustment(s) and validate the cost and depreciation schedules used in the cost programs, modifying these schedules where necessary.

The third phase of residential/farm/vacant valuation will employ the comparable sales approach using the sales that have been identified and verified for the municipality.

For properties where sufficient sales information exists, the contractor will develop preliminary market valuation models.  However, before any valuation testing begins, a list of all sales to be used must be reviewed with the project administrator.  Sample properties will be valued and the results are to be reviewed by both the contractor and the municipality.  The model(s) must be adjusted and the sample rerun until optimum results are obtained.  All models will be subject to review by ORPTS for statistical and logical accuracy.

If the market approach to value is not feasible for determining defensible values for farm parcels, the contractor must propose an alternative method of determining values.  Also, the contractor must provide a parcel listing with an estimate of value for each agricultural building upon which an exemption has been granted.

4.11.2  Commercial/Industrial

The commercial/industrial valuation module of the NYSRPS or an equivalent system that incorporates market, income, and cost valuation techniques will be used.  The municipality and the contractor, with the advice of the ORPTS, will mutually agree on the amount of income and expense data that is complete and representative of the universe of commercial/industrial properties.  [Depending on the number and relative complexity of the municipality’s commercial parcels, does the municipality want to consider engaging the services of a commercial appraiser with local knowledge to serve as a resource to both the Assessor and the contractor for this project?  If so, mentioning this in the RFP may be appropriate, particularly if, as a consequence, the municipality would expect adjustments to the contractor’s proposed pricing.]

4.11.3  Unique and Highly Complex Parcels

The project administrator and the contractor will attempt to isolate the unique parcels and highly complex properties at the outset of the project.  Appendix B contains a list of known unique and highly complex properties.

If the property cannot be valued using a computerized mass appraisal system, the contractor will assign an appraiser to apply appropriate appraisal methodology, and provide a brief, 2-3 page limited summary narrative appraisal for these parcels.

The key elements that are to be shown in the limited summary narrative appraisal are:

- a complete inventory including copies of property record cards;

- sketch;

- photograph(s);

- description of property;

- delineation of the area;

- land valuation;

- cost valuation;

- market approach, if appropriate;

- income approach, if appropriate;

- correlation of values; and

- reference manuals used

The company shall submit with its proposal the qualifications / resume of the person(s) who will actually value the unique and highly complex parcels.

4.11.4 Condominiums and Cooperatives (as applicable)

Pursuant to New York State Law, each cooperative complex receives a single assessment and shall be valued pursuant to an income approach to value (utilizing hypothetical rental income), analogous to the valuation of an apartment complex, as if the complex were not owned in cooperative form.  In addition to providing such valuation, the contractor should provide the municipality with a spreadsheet indicating a proportional breakdown of unit values from said total value for purposes of exemptions and other administration.

Pursuant to New York State Law, condominium complexes in the municipality are currently also valued pursuant to an income approach to value, however each unit receives an individual assessment (in contrast to cooperatives).  As part of a reassessment and approval of same by ORPTS, the municipality will have the option to consider assessing condominium units (not cooperative units) as if they are residential property (Property Class 210-C and / or 411-C) and not subject to the income approach but rather according to actual market value of the units (the Homestead Tax Option). The contractor’s proposal shall assume that condominium units will be individually valued / assessed based on the current income approach to value as if the complex was not held in condominium form.  In addition to the income based valuation, the contractor must also provide sale based values for all residential condominiums (those units that would be classified as Homestead).  [The municipality should determine if it wants market based values for all condominium units as a reference regardless of homestead classification.]  The field review of these values must be completed in the same time frame as the field review for all other parcels as they are necessary for analysis of the Homestead Tax Option as part of the assessment disclosure process and the municipality’s decision making on the adoption of Homestead.  [Delete this section if it is not pertinent to the municipality issuing this RFP.]

4.11.5 Valuation Reports

Throughout the scheduled valuation, copies of valuation processing summary reports are to be given to the project administrator within three (3) workdays of report production.

This includes reports from the market valuation programs (5-10 page samples, weights and coefficient adjustments only).  Also, a copy of any other valuation reports run must be given to the project administrator.

Additionally, all Residential, Farm and Vacant (R/F/V) parcels valued through the valuation system, utilizing the market value approach, must have an accompanying valuation report showing a selected description, to include all appropriate value items as indicated in the sales analysis, for each subject and comparable sales parcel.  At least three (3) of the most comparable sales are to be identified for each subject parcel.  If utilized, a model estimate and weighted estimate are to be shown for each subject parcel.  The photographic images of the subject and each comparable sale may be displayed on the comparable sales valuation document.  [The display of photographic images of the subject and each comparable sale on the comparable sales valuation document is strongly recommended.]

All commercial and light industrial parcels valued through the market and income system must have an accompanying valuation report showing a description of the parcels' uses by square feet or units and two estimates of value:  market and simple mortgage equity capitalization of income.

4.12	Field Review

The contractor is responsible for 100% field review of all value estimates including vacant land and wholly exempt properties.  Field review is to be conducted from the nearest public road or public right of way from which the property is visible.  Field review is to be completed by a qualified field reviewer in accordance with the Field Review Manual published by NYSDTF - ORPTS.  Parcels are to be valued as of the valuation date for the tentative roll.  [The contractor may propose a field review at least, in part, from the images assembled for this project.  The municipality should consider language for this RFP that speaks to the acceptability of this possible process.  Use of images for field review may save time and some cost but may also have some negative effects on the public’s perception of the resulting values.  For purposes of qualifying for State aid, photographic imagery may only be used in an office review if the photography is within three years’ currency.  Please note that satellite imagery (e.g., Google Earth, Bing, etc.) does not qualify for use in an office review.]

Final values are the responsibility of the municipality's Assessor(s).  The contractor, when changing machine-generated value estimates, must enter the proper explanation on the field review document.  Typical explanations would include data inaccuracies, unique subject property, Assessor’s override, etc.

Prior to field review, the municipality and contractor must agree on documentation procedures for those parcels with significant changes in value, defined as a XX% variation between the computer generated estimate and the field reviewed value.  [Project administrator / Assessor will determine with contractor’s input which computer generated value will be used as the basis for comparison.]   In addition, the contractor shall provide a report by appropriate grouping (e.g., neighborhood, tax map section), in a mutually agreeable format listing (e.g., GIS map) the % change between the full value indicated on the latest final assessment roll and the preliminary value resulting from field review for all parcels.  [Ensure this is consistent with how variation is defined in section 3.1.4.]

Prior to informal review meetings, the contractor must record on the field review document all value changes that occur due to data error, and reflect the data changes on the data file for that parcel.

The Assessor must make every effort to participate fully in the field review process.  It is imperative that the municipal officials attain a complete and thorough understanding of field review in general, and more specifically, the determination of value process.  [The municipality should support and encourage the active participation of the Assessor and Assessor’s staff with the contractor in the field review to the degree possible.  Given the local knowledge of the Assessor and Assessor’s staff, valuation issues can be identified and corrected prior to the mailing of assessment disclosure notices / informal review meetings.  In turn, this can prevent negative perceptions about the project by minimizing more obvious and glaring valuation errors.]

4.13	Assessor’s Value Review

The Assessor or the Assessor’s designee(s) will be involved in the review of values throughout the field review phase of the project. All contractor-produced values are to be entered on the data file and given to the Assessor for final value review prior to the Assessor’s value review date specified in the project timetable of this RFP.

Since the defense of values will be the responsibility of the contractor, any requests for changes to the contractor's values must be made in writing to the contractor.  The Assessor's value and the appropriate Assessor’s override code designating the reason for the change must be applied to the mechanized file.  This relieves the contractor of any responsibility to defend such changes.

4.14	Assessment Disclosure Processing / Tax Shift Analysis

The county/contractor is responsible for producing assessment disclosure notices to be sent to all property owners.  In accordance with RPTL Section 511, assessment disclosure notices must be mailed sixty (60) days prior to tentative roll date.  A minimum of 20 workdays is required to accomplish this processing; therefore, the municipality must deliver a computer file to the county/contractor (complete with value entries for all parcels in all roll sections) by the date specified in the project schedule. The municipality is also responsible for providing a prior year assessment computer file in addition to verifying the prior year, extended roll totals, the levy rates, and the total tax levies to be used.

The contractor will assist the municipality with advice from ORPTS in composing a cover letter to accompany the assessment disclosure notice.  This letter will provide further background about the project, the informal review process, the forthcoming tentative roll and grievance process, and the use of the new assessments in levying upcoming taxes.  [Please note that assessment disclosure processing is required if the state equalization rate for the immediately preceding assessment roll was less than 85.00.  While a municipality is not obligated to produce assessment disclosure notices if the prior state equalization rate is 85.00 or higher, the municipality may still consider producing these notices as part of its public education program.

If assessment disclosure will be performed, the assessment disclosure notice will be the property owner’s first exposure to their new preliminary assessment.  Does the municipality want to have any additional material mailed with the disclosure notice and the cover letter (e.g., the property specific valuation documents or a web link and password to a project related website where those documents could be viewed)?]

The assessment disclosure processing agent is responsible for providing the municipality and ORPTS with the results of the tax shift analysis _______ days in advance of any municipal public meeting at which these results will be discussed for prior review. [Tax shift analysis should be performed regardless of whether assessment disclosure notices are to be mailed.  The assessment disclosure programs in RPS will produce a tax shift analysis although the municipality may choose not to mail individual notices to property owners under the conditions noted above.  If the municipality chooses not to produce / send individual assessment disclosure notices, it must determine if it wants the contractor to produce a tax shift analysis through the assessment disclosure programs in RPS or whether it wants to define the scope of tax shift analysis to be produced through other means.]

[If this project includes consideration of the adoption of the Homestead Tax Option, it is strongly recommended the municipality discuss the adoption process with ORPTS’ staff as part of the customization of this RFP.  Assessment disclosure processing / tax shift analysis will require additional work to produce the analyses needed for the municipality to make an informed decision about its use of Homestead.]

4.15	Informal Review Process

All property owners have a right to an informal review.  All property owners who make an appointment within the agreed upon time period will receive a meeting to discuss the preliminary value.  The contractor must inform property owners at the meeting that a notice of results will be mailed to them.  The informal review process is the responsibility of the contractor.  [The Assessor and the Assessor's staff are strongly urged to participate.]  The contractor will provide staff to receive property owners' telephone calls, answer questions and set up appointments by telephone for meetings.  The contractor must use experienced field review staff for these meetings and for fieldwork related to property owner inquiries.  This includes the responsibility of re-inspection and data correction processing to the assessment/inventory files.  [The municipality should determine prior to the issuance of this RFP whether it would entertain an informal review process that is performed through a telephone or web-based system, including email, as opposed to the traditional system of face-to-face meetings described in this RFP.]

Scheduling of evening/weekend meetings, in addition to the daytime schedule, will be required.  Meetings will be pre-scheduled by telephone and held at sites to be determined later.

The contractor must inform the property owner at the time an appointment is made and at the start of each informal review meeting, that the purpose of the informal review meeting is to explain how the preliminary value is set; that no decision regarding a property’s value will be made at the time of the informal review meeting; and, that a notice of the results will be mailed to the property owner after the information presented and any follow up investigation has been reviewed.

The contractor must provide the municipality with an analysis of and a GIS map of, at least, the following:

- number of informal review meetings;

- number of informal reviews resolved in session;

- number requiring "in-field" follow-up;

- number requiring inventory changes; and

- amount of assessed valuation changed, by property type

4.16	Value Change Notice (Section 511 Notice)

As a result of value changes made during the informal review phase, the municipality is required to send out a change of assessment notice to the owner of all parcels where a meeting was conducted or where a value has changed between the issuance of the assessment disclosure notice and the tentative assessment roll.  The municipality/contractor will be responsible for envelope stuffing, postage, and mailing of these notices.

4.17	Formal Defense of Values

During the formal grievance period resulting from the publication of the tentative assessment roll, the contractor, upon request, must make individuals with appraisal and field experience available to assist the Assessor(s) in presentations to the Board of Assessment Review.  The contractor will be responsible for performing all related fieldwork, valuation justification / documentation and for processing inventory changes resulting from grievance proceedings.

The contractor will be responsible for representing the municipality in all certiorari proceedings resulting from the final assessed values which the contractor made and which were placed on parcels on the final assessment roll and only if that grievance has been filed prior to or on grievance day.  The contractor will be required to assign skilled personnel who are familiar with the project and experienced in court testimony.  As the volume of these actions is impossible to predict, this function is not considered to be part of the contractor's fixed price proposal.  [Municipality should state any expectations as to the level of experience, licensure and / or other qualifications of contractor staff who would provide these services.]

All proposals should specify the amount to be charged to the municipality on a per diem basis, for defending values during the small claims and certiorari hearings, inclusive of field analysis.  [Ensure that this is consistent with the grid breakdown in Section 10.]

4.18	Project Status Control

The successful completion of this project depends upon proper coordination, planning and management throughout its duration.  Therefore, the contractor must:

Provide summaries of project status to the project administrator and ORPTS (Municipality to insert example of status report contents) on a _______ basis [at a minimum, monthly].  These reports will present accurate up-to-date project status; specifically contractor progress, possible problem areas, remedial measures that are being undertaken, overview of contractor staff participation, and training provided to municipal staff.

Attend meetings, held on a               basis, [at a minimum, monthly], with the project administrator to review project developments, resolve problems, interpret contractual requirements, review billings, and provide project continuity.  The project director, appropriate staff, and ORPTS will attend these meetings.

Attend meetings, held on an as needed/requested basis, with the project administrator.  These meetings will be similar in content and conduct to the regular meetings.  The project director, appropriate staff and ORPTS will attend these meetings.

Provide miscellaneous written reports regarding specific project developments, as they arise, to the project administrator.

4.19	Submissions for State Aid/Value Verification

The contractor assembles and provides documentation to the municipality for reimbursement for State aid pursuant to the Rules as well as the documentation required for value verification as outlined in the Memorandum of Understanding between NYSDTF – ORPTS and the municipality (see MOU).

4.20	Mass Mailing and Postage

The contractor / municipality is responsible for providing paper, envelopes, and postage (first class) relative to mailing each of the following:

- pre-inspection letters;

- property description reports (aka data mailers), including cover letters;

- request for commercial income and expense statements; and

- assessment disclosure notices necessary for this project

The contractor / municipality will be responsible for folding, stuffing and addressing all mailings.

4.21	Data Entry

The contractor is responsible for providing data collection and valuation related data entry services as necessary.

The final output of the data entry device must be on media that is machine-readable at the file creation site.  The media is to be provided by the contractor.

The contractor may opt to utilize an on-line update feature and place the data inventory changes directly onto the inventory file.  This procedure satisfies the requirements of this section.

4.22      Valuation Documentation

A preliminary USPAP compliant Mass Appraisal (Reassessment) Report shall be provided to the municipality prior to mailing change of assessment notices.  A final USPAP compliant Mass Appraisal (Reassessment) Report shall be expected within two (2) weeks after publication of the final assessment roll. [Include sample in Appendix G.]

4.23	Option - Updating of All Values for the Post-Reassessment Year Roll

In order to maintain the level of assessment equity reached as a result of project activities, for the subsequent          assessment rolls, the contractor shall specify an optional annual addition to the contract.  This shall detail the valuation and data collection procedures that would be employed should the municipality seek to use the contractor’s services to maintain the post-reassessment years’ values.  The contractor shall further specify the latest date by which the municipality may notify the contractor of its desire and intention to exercise this option. [The municipality must specify the level of service desired for each year in which a price is sought.]

The contractor shall itemize and specify the cost of this option at the time of this RFP.

SECTION 5 - DATA SECURITY

The contractor is responsible for establishing and maintaining appropriate methods to store and transport all project data in a manner that will ensure minimal data loss.

Each company will submit a plan for data security in its proposal.

The contractor will be responsible for copying each master data file and all project related databases (e.g., commercial income and expense data, photographic images, etc.), at a minimum, on a weekly basis, and storing them on-site and in an off-site location that will ensure safety of the files.  The transactions necessary to update the data files, will be kept on appropriate data storage media until the updated master file is copied.  This will be in addition to the normal daily and weekly archiving, the results of which need not be stored off-site.

The contractor shall not keep, copy, use or take away from the municipality any document, paper, computer output, or other material to which the contractor obtains access during this project.  The contractor shall not at any time reveal to any person outside the scope of this project any proprietary or confidential information of which the contractor gains knowledge during this project.  The contractor shall, at the termination of the project, return to the municipality all identification badges, keys, or other access devices issued by the municipality and shall not copy or use any such devices in any manner except as specifically authorized by the municipality.

SECTION 6 - CONTRACTOR PROJECT STAFFING

The contractor must provide competent professional and technical personnel who are capable of accomplishing the required work.  The company will, in its proposal, describe the organization structure that will be used to manage this project and will include a complete organization chart.  All management and technical personnel that the contractor will use for the project must be approved by the project administrator prior to assignment and must be named in accordance with the following:

6.1	Project Management and Technical Staff

Contractor staffing for this project should include, at a minimum, the following:

- Management Staff

  - Project Director

  - Data Collection Supervisor

  - Data Management Supervisor

  - Office Manager

  - Public Information Officer

- Technical Staff

  - Data Collectors

  - Crew Chiefs

  - Personnel who will be responsible for assessment, inventory and valuation processing

  - Personnel with residential/farm/vacant valuation responsibilities

  - Personnel with commercial valuation responsibilities

  - Personnel with training responsibilities

  - Qualified Field Reviewers

  - Property Owner Inquiry Specialists

[For which specific personnel proposed does the municipality want to see resumes?]

The contractor must make at least one technical person available for assessment/inventory processing, as needed, throughout the project.  At least one person, skilled in the operation of the valuation programs, will be required during the valuation phase of the project.

A minimum of the project director, one technical person, and sufficient appraisal staff will be required to provide services as needed.

The name of the individuals who will direct, supervise, and furnish technical assistance; their qualifications, the staff days each will spend on the project, the time each will be spending on other concurrent projects, and a list of the most recent projects in which each has been involved, identifying the capacity in which they were employed, must be in the proposal.

6.2	Staffing Changes

If the contractor needs to make a change in staffing, the contractor must obtain approval from the project administrator and then notify ORPTS upon the project administrator’s approval.   The contractor must make every effort to maintain the specified staff or staff with equivalent training and experience.  The contractor cannot be responsible for personnel changes beyond its control.

SECTION 7 - DELIVERABLE PRODUCTS

The contractor will be responsible for the delivery of the following products according to the project timetable:  [Specify target dates for all deliverables and include these products as part of the USPAP Compliant Mass Appraisal (Reassessment) Report Documentation.  See the IAAO Mass Appraisal Revaluation Template attached to this RFP for potential format in which you can have a vendor document products and services provided as part of the reassessment. A summary/narrative description of certain products can be included in the documentation if approved by the municipality.  The municipality must review the list of deliverables below to ensure it matches the specific products and services described in this RFP. ]

- Project status reports produced throughout the project;

- Training lesson plans, timetables, dates of training, attendance rosters, and Assessor sign off on training components;

- Sample sales verification letter/mailer for Assessor sign off;

- Sample income & expense questionnaires for Assessor sign off; originals of all returned forms;

- Sample inventory property description report / data mailer or Website Design for all property types for Assessor sign off; originals of all emails or returned forms;

- A data collection form or data collection device design with sketch (and photograph/images, if this option is selected) for each parcel;

- A copy (computerized or paper) of all valid sales used in valuation and all documents required in Section 4.9;

- A report and GIS Map Displays of failures and discrepancies in the accuracy of data items collected, as revealed by the recollection of data items by field supervisors/crew chiefs and a report of the remedial action taken;

- A report of all tax map discrepancies found;

- A GIS generated neighborhood map for all residential and non-residential neighborhoods / valuation groupings along with a narrative that defines each neighborhood or grouping;

- Valuation processing outputs including all selected options used for regression and comparable sales routines (computer file and paper or electronic copies); also including, but not limited to, a copy of variables and options used for land, cost, market and income;

- All manual and computerized reports that support values and valuation formulae including but not limited to: sales ratio studies, CAMA models, unit price analyses (i.e., $/sq. ft., $/acre, etc.);

- A computer-produced comparable sales report for each R/F/V parcel valued using the market approach; a copy of all comparable sales reports must be provided to the municipality prior to the start of field review in order to aid the Assessor in reviewing the computer generated values;

- A computer-produced market and income report for each commercial parcel valued; a copy of all market and income reports must be provided to the municipality prior to the start of field review in order to aid the Assessor in reviewing the computer generated values;

- A field review one-liner for each parcel appraised (R/F/V and commercial);

- A copy (computerized and paper) of the valuation factor file or equivalent used to produce commercial market and income values (to include but not limited to: gross income per unit, vacancy rates, expense ratios and capitalization rates); all income and expense data used to produce the valuation factor file including (but not limited to): questionnaires returned by commercial property owners, market, lease and/or sales data used from within or outside of the municipality and copies of any published market data used;

- Land schedules and sales analysis documentation used in the land valuation effort;

- A written overview report of valuation methods used;

- A limited summary report for each unique or highly complex property;

- A cross reference of values, i.e., a listing of estimates of values for each parcel as of tentative roll;

- Original field review documents for all parcels including cost, comparable sales information and market and income information with field notes justifying all adjustments from the machine-generated estimates;

- A report of the reasons for significant changes made to machine-generated estimates of value resulting from field review, and all changes resulting from informal review meetings with property owners or any other action by, or on behalf of, the municipality;

- A preliminary municipal master file containing all preliminary assessments and all inventory used as the basis for the preliminary assessments for the purpose of assessment disclosure production and ORPTS’ analysis (if the municipality or the contractor are not using RPS V4 for processing, this file must be made available to ORPTS in a RPS V4 compatible format);

- As of tentative roll, a sales ratio study showing the ratio of sales to assessed values of recently sold parcels in the assessing unit (see glossary for definition of ratio study), plus any other analyses used to validate the tentative assessments;

- A report on the disposition of all property owner complaints and informal reviews;

- The following programs will be run in the prescribed sequence in order to assure that the subject and sales inventory data and associated output reports turned over to the municipality are as clean as possible:

  - Inventory Editing - A program which performs standard and/or user defined cross edits (see Section 4.10) on the residential and commercial inventory files.  The output report must show that all possible edit errors have been resolved, or else maintain the master files to resolve errors and re-run until all edit errors have been resolved; and

  - Sale/Subject Mismatch - A program which compares the subject inventory to sale inventory and displays mismatches.  The output report must show that all erroneous mismatches have been resolved, or else maintain master files to resolve errors and re-run until all possible edit errors have been resolved.  Copies of these files must be available to the municipality prior to final valuation production;

- One copy of the municipal master file, complete and up-to-date, used to produce the tentative assessment roll as described, including inventory for all parcels used as the basis for the tentative assessments, as well as all sales used in the analysis for this project and the associated inventory at time of sale (if the municipality or the contractor are not using RPS V4 for processing, this file must be made available to ORPTS in a RPS V4 compatible format);

- One copy of all the documentation and application(s) prepared for the municipality for submission to ORPTS for applicable state aid reimbursement; one copy of all documentation prepared for ORPTS as part of its value verification process;

- Training for municipal assessment staff and Board of Assessment Review as specified in this RFP has been completed as evidenced by attendance logs and sign-in sheets.

- All items specified in the “Reassessment Verification Documentation” attachment of the Guidelines for Cyclical Reassessment must be provided to ORPTS’ project liaison as soon as each becomes available to the Assessor.

- In the event the municipality exercises its option to seek a post reassessment update of all values for the next subsequent tentative assessment roll(s), all items pertaining thereto shall be specified by the contractor herein, pursuant to Section 4.22 herein.

- Any item cited in the above RFP narrative and not included in this list of deliverable products.

The contractor's work shall be considered to be complete and meeting final acceptance when all of the items mentioned above in Section 7 are delivered as part of a USPAP compliant Mass Appraisal Report, to the project administrator and are certified as complete and accurate by the project administrator.

Within 30 days of receipt, the project administrator must notify the contractor in writing that the contract is complete or supply a list of missing deliverables.  The number of copies of final computer data files and program work flow (paper copy) will be limited to one machine-readable copy of each.  System documentation and completed data collection instruments will be limited to one (1) copy.  Copies of written materials, such as work plans and reports to be furnished to the municipality which is considered suitable and necessary in the opinion of the municipality's project administrator will be delivered.  The contractor will retain copies for one year of any work products that have been approved by the project administrator.  During this time frame, these products will be available at no expense to the municipality.

SECTION 8 - PAYMENT SCHEDULE AND PENALTY

With the exception of per diem charges for work related to small claims and certiorari proceedings, this is a fixed price contract.  Proposals submitted, other than fixed price proposals, will not be accepted.  Each proposal shall include a payment schedule that shows deliverable products at easily identifiable stages of the project.  Payment shall be made to the company, according to the agreed upon schedule, for the pro-rata share of the itemized cost of each task and phase of the project based on the percentage of completion of that task or phase.  The schedule is to adhere to the following criteria.

The contractor will submit an itemized bill to the project administrator.  This bill is to be discussed at the next regularly scheduled status meeting.  The project administrator shall review submitted vouchers within two weeks of receipt.  The project administrator must notify the contractor, in writing within an additional week, of any item or portion of an item that is incomplete, not in conformance with the contract, or erroneous.  If the project administrator certifies that the project is progressing satisfactorily in accordance with the project timetable (Section 4.2 of this RFP), payment for the uncontested items will be made to the contractor representing eighty percent (80%) of the amount billed.  The remaining twenty percent (20%) will be retained by the municipality.  The entire amount so retained will be paid to the contractor within thirty (30) days following satisfactory completion of the terms of the contract.

If the project administrator determines that, due to the fault of the contractor, the project is not progressing satisfactorily on schedule, an additional forty percent (40%) of the bill will be retained.  The project administrator will provide the contractor with written justification for the additional retainage and define an acceptable resolution to the situation.  If the problem has been rectified to the satisfaction of the project administrator within thirty (30) days, the forty percent (40%) will be paid at that time.  If the problem is not rectified within the thirty (30) day calendar period, the project administrator will immediately determine whether the forty percent (40%) or a portion thereof will be retained until thirty (30) days after satisfactory completion of all terms of the contract; or, whether the municipality will exercise the option of having the work satisfactorily completed at its own expense and the cost thereof deducted from the retainage.

[The municipality may wish to consider adjusting the retainage as described in the previous paragraphs.  The municipality’s Attorney should be consulted.]

SECTION 9 - CONTRACTUAL REQUIREMENTS

The following constitute legal and insurance obligations with which the contractor must comply and which constitute the minimum of said requirements to be incorporated in the reassessment contract.

9.1	Rules and Procedures

The contractor must affirm it will conduct this project in strict compliance with the Rules and procedures and provide all products as described in the Project Verification Documentation list to the Assessor/project administrator and ORPTS’ project liaison so as to facilitate the timely verification of this reassessment.

9.2	Employment Requirements

The contractor shall comply with all the applicable provisions of Federal and State laws, rules and/or regulations regarding employment, and will further specifically comply with those sections related to discrimination as follows:

In hiring of employees, for the performance of work under the reassessment contract, or any subcontract hereunder, no contractor or subcontractor shall by reason of race, age, sex, color, creed, or national origin, discriminate against any citizen of the State of New York who is qualified and available to perform the work to which the employment relates.

No contractor, subcontractor, or any person on his behalf shall, in any manner, discriminate against or intimidate any employee hired for the performance of work under the reassessment contract by reason of race, age, sex, color, creed, or national origin.

In the event the contractor breaches any of the terms set forth herein with regard to discrimination, or violates the New York State Labor Law, as last amended, during the pendency of this agreement, there may be deducted by the municipality the legally designated penalty for each person for each calendar day during which such person was discriminated against, or intimidated, in violation of the provisions of this agreement, from the fixed price heretofore set in to be paid to the contractor.

The reassessment contract may be canceled or terminated by the municipality and all monies due or to become due may be forfeited for a second or any subsequent violation of terms or conditions of this section of the reassessment contract.

All project personnel must be approved by the municipality prior to being employed for the project and will be required to carry an identification card while on project business.  This I.D. card will contain the employee's photograph, name, title and physical description.  This card will carry the signature of the project administrator and will be issued by the municipality.  This card will be surrendered to the project administrator upon termination of the employee or upon completion of the project.

9.3	Changes in Contract

There shall be no changes, alterations, or additions in the reassessment contract without prior written consent of the municipality's contract administrator.  This specifically includes the fixed price payment and per diem charges as outlined in the contract.

In the proposal, the company will state that the fixed price paid by the municipality to the company shall include any and all expenses set forth by example herein, but not limited thereto, including all temporary living and relocation expense allowances, nominal office supplies, direct and indirect costs, administrative and marketing overhead, and travel within the municipality.  The said fixed price also includes expenses of the company, its agents and/or employees for travel outside the municipality.

9.4	Statement of Non-collusion

A statement of non-collusion, duly executed by the company, shall be affixed to the offer to perform services pursuant to this contract, and shall affirm that:

The proposed fixed price has been arrived at independently, without collusion, consultation or communication as to any other company or with any competitor.

The said fixed price was not disclosed by the company and was not knowingly discussed prior to the submission, directly or indirectly, to any other company or to any competitor.

No attempt was made by the company to induce any other person, partnership or corporation to submit or not to submit a proposal for the purpose of restricting competition.

Appendix C contains a sample of an affidavit for this purpose.

9.5	Insurance Requirements

The municipality and the contractor must mutually understand and agree their respective liability hereunder for damages, regardless of the form of proceeding or action, shall be such as is defined by applicable statutes and common law of the State of New York.

The contractor will serve in the capacity of an independent contractor in this reassessment project and will maintain insurance at least as hereinafter set forth so as to protect it and the municipality from any and all claims under the Workers’ Compensation Law, and such other employee benefits law, and from claims for damage to person or property arising out of and during its operation pursuant to this agreement, for the entire pendency of this reassessment project:

- A comprehensive general liability insurance policy with the following limits of coverage: bodily injury and property damage, $1,000,000 each occurrence, $1,000,000 each individual claim per occurrence, $1,000,000 aggregate of all claims per occurrence.  [Are the insurance requirements in this and the next bullet sufficient in the estimation of the municipality’s Attorney?]

- A comprehensive automobile insurance policy with the following limits: bodily injury, $1,000,000 each person and $1,000,000 for each occurrence; property damage, $1,000,000 each occurrence, aggregate $1,000,000 for each occurrence.

- The foregoing comprehensive liability insurance policy and comprehensive automobile liability insurance policy shall include the municipality as an additional named insured, at no extra cost to the municipality, and the certificate of the insurance relating hereto shall be submitted to the municipality upon the signing of the contract.  The contractor, in addition to the foregoing, must provide and maintain, during the pendency of the reassessment project, such Workers’ Compensation and Employer Liability Insurance and New York State Benefits Insurance policies as are required by statute.  An insurer licensed and authorized to do business in the State of New York that maintains an office within the State of New York must issue all of the insurance.

9.6	Conflict of Interest

No director, officer, employee, agent, contractor, or subcontractor of the contractor shall be deemed to be an agent, servant and/or employee of the municipality.  The contractor shall not employ as a director, officer, employee, agent, contractor, or subcontractor, directly or indirectly in any capacity, any elected or appointed official of any city, town, village, hamlet, school district, or other political subdivision of the municipality or any member of the immediate family.

The contractor agrees it will require all its directors, officers, employees, agents, contractors, or subcontractors, to be bound and adhere to the Code of Ethics of the municipality (See Appendix A of this RFP).  The contractor further agrees it will require all of its employees to comply with all applicable laws relating to this agreement and it will provide relevant testimony regarding any phase of this agreement, or the performance thereof, and the refusal to supply such evidence and/or testimony shall be the cause for immediate termination of this agreement by the municipality.

9.7	Assignment of Contract

The contractor shall not assign, convey, transfer, or delegate any of its responsibilities and obligations to this agreement to any person, corporation, partnership, association or entity, without the prior written approval of the municipality's contract administrator.

9.8	Compensation

The contractor will follow the procedure outlined in Section 8 of this RFP for payment.

9.9	Ownership of Work Products

All final written or tangible work products shall belong to the municipality.  In the event of premature discontinuation of work, the contractor shall agree to provide all existing work and data files to the municipality.  Delivery of all files after the project is completed will be as outlined in Section 7 of this RFP.

9.10	General Legal Responsibility

The contractor must comply with all federal, state, and municipal laws, ordinances, rules and/or regulations, including labor laws, and those against discrimination, existing or adopted in the future, during the term of the project, applicable at any time to the contractor pursuant to its obligations in regard to this project.  The contractor and any of its subcontractors, agents, servants, and/or employees shall obtain, at their sole cost and expense, all required permits, franchises, approvals, licenses and/or certificates, necessary for the performance of its obligations pursuant to the agreement.

9.11	Instrument of Contract

The contract must specifically set forth in the body thereof or in an appendix thereto the duties and responsibilities of each of the parties.  A combination of the request for proposal and the proposal would be sufficient for this purpose.  Beware; this practice could give rise to disputes as to exactly what was agreed upon by the parties.  The precise terms and conditions must be explicitly set forth.  In most cases this could best be accomplished by preparing a contract which prioritized all of the documents and merges them so as to reflect exactly the agreement and understanding of the parties and which details such other areas of agreement as may have been reached during negotiations.  The RFP will become the senior document and the company proposal will become the junior document.  This instrument of contract will be agreed upon and signed prior to project commencement, no later than date.

9.12 	Disputes - Venue and Jurisdiction

The parties to the contract hereby agree the Law of the State of New York shall be the governing law in any dispute that may arise under this contract, regardless of location of principal place of business and / or state of incorporation of company providing services hereunder.  In addition, the parties consent that the result of any and all litigation which may arise out of any dispute concerning this contract shall be venued in the Supreme Court of the State of New York, County of ___________.  The parties expressly waive rights to a jury trial for any and all disputes that may arise concerning this contract.  In any such proceeding or litigation, the prevailing party shall also be entitled to recover its costs, disbursements and reasonable attorney's fees incurred therewith.

SECTION 10 - PROJECT COST ITEMIZATION

The following schedule must be used to itemize project cost.  Additional entries may be made where appropriate.  Also, the intended use of a subcontractor for any or all work to be performed within the scope of this project must be stated separately.

[For individual municipalities and all municipalities in total, e.g., a Consortium, and each individual municipality]

| CATEGORY | AMOUNT |
| --- | --- |
| Project Management (including RFP Sections 4.3, 4.4, 4.5, 4.6, 4.7, 4.20, 5, 6, and 7) |  |
| Public Relations (RFP Section 4.3) |  |
| Data Collection (including RFP Sections 4.8, 4.9, and 4.10) |  |
| Valuation Analysis and Production (RFP Section 4.11) |  |
| Field Review (RFP Section 4.12) |  |
| Informal Review Meetings including BAR (RFP Section 4.17) |  |
| TOTAL |  |

| Options |  |
| --- | --- |
| Photo/Images |  |
| Scanning of Documents |  |
| Public Utility Property |  |
| -Structural |  |
| -Non-Structural |  |

| Per-diem Charges |  |
| --- | --- |
| Additional Classroom Training/Workshops |  |
| Small Claims |  |
| Certiorari Report Preparation |  |
| Certiorari Court Testimony |  |

APPENDIX A – Municipality Code of Ethics

APPENDIX B – Unique or Highly Complex Parcel List

[At a minimum, include the breakdown of waterfront property by property class.  Unique or highly complex properties may include parcels that are wholly exempt.]

APPENDIX C – Affidavit

____________________________________, being duly sworn, deposes and says:

(NAME)

1.	He was, and continues to be,

________________________________, ________________________________.

(TITLE)                                                		  (FIRM NAME)

2.	He is familiar with the attached proposal for professional service for

________________________________________________.

(NAME OF MUNICIPALITY)

3.	The proposed fixed price has been arrived at independently, without collusion, consultation or communication as to any other company or with any competitor.

4.	The said fixed price was not disclosed by the company and was not knowingly discussed prior to the submission, directly or indirectly, to any other company or to any competitor.

5.	No attempt was made by the company to induce any other person, partnership, or corporation to submit, or not to submit, a proposal for the purpose of restricting competition.

_______________________________________________

(SIGNATURE)

Sworn to before me this ___________ of ____________________, ____________

(DAY)                       	       (MONTH)        	               (YEAR)

_______________________________________________

(NOTARY PUBLIC)

APPENDIX D – Sample Proposal

SAMPLE

Contractor

Proposal

in response to the

Request for Proposal

Real Property Reassessment Project

Municipality

New York

Date

Each proposal must be organized as follows and include, but not be limited to, all of the following items:

- A brief introduction stressing the company’s strengths as well as its commitment to quality.

- A statement of the company's full compliance with the Rules and the provision of all products as described in the Reassessment Verification Documentation list of the Guidelines for Cyclical Reassessment to the Assessor / project administrator and ORPTS’ project liaison so as to facilitate the timely verification of this reassessment.

- A statement of the company's full compliance with the Guidelines for Cyclical Reassessment so as to maximize the likelihood that the municipality will qualify for Aid for Cyclical Reassessments.

- A complete client list of all real property related projects with which the company has been associated over the past             years.  [Typically five years, but could be more or less.] A contact person and telephone number for each project must be listed.

- A detailed outline, and schedule, by project phase, of the company's intended public relations endeavors.

- A specific training schedule that the company intends to follow during the project.

- A description of a detailed quality control program.  The program must include a comprehensive weekly reporting procedure to the municipality that details collection staff, each collector's work, town level progress summaries and estimates for the upcoming week.

- If a photo or image option is being proposed, a description of the equipment to be used, and a discussion of the method of identification used to ensure the link of images to corresponding parcels.  The company must provide a detailed list of all equipment and associated cost, i.e., hardware, software, imaging devices, which will be utilized at the municipal level for viewing, printing images, and updating.  A description of how the imagery will be used for the collection and/or verification of inventory must be provided.  The contractor shall provide an outline of the training program for municipal staff in the implementation and operation of the image system as well as a description of the procedures and the associated cost with updating the image file.  The company must describe its procedures for linking the video images to the file.

- A detailed plan for data security.

- The organization structure that the company will use to manage this project and will include a complete organization chart.  The name of the individuals who will direct, supervise and furnish technical assistance; their qualifications, the staff days each will spend on the project, the time each will be spending on other concurrent projects and a list of the most recent projects in which each has been involved, identifying the capacity in which they were employed, must be in the proposal.

- A statement that the proposed fixed price to be paid by the municipality to the company shall include any and all expenses set forth by example herein, but not limited thereto including all temporary living and relocation expense allowances, nominal office supplies, direct and indirect costs, administrative and marketing overhead, and travel within municipality.  The fixed price must include expenses of the contractor, its agents and/or employees for travel outside the municipality.

- A statement of non-collusion, duly executed by the company, must be affixed to the offer to perform services pursuant to this contract, and must affirm that:

  - The proposed fixed price has been arrived at independently, without collusion, consultation or communication as to any other company or with any competitor.

  - The said fixed price was not disclosed by the company and was not knowingly discussed prior to the submission, directly or indirectly, to any other company or to any competitor.

  - No attempt was made by the company to induce any other person, partnership or corporation to submit or not to submit a proposal for the purpose of restricting competition.

- A statement of the company's full compliance with the specifications found in this RFP and a Company Proposal Response Grid (see below).  All companies must enter a response in Column B for every section of the RFP listed on the grid.  If a conflict arises between the internal wording of the company proposal and the section indicated on the response grid, the response on the grid shall be considered the intent of the company.

If the company is offering goods and / or services above and beyond the minimum standard specified in the RFP, enter the appropriate response in Column C and corresponding cost (if any) to the municipality for adopting this option.  Column C must also reference a detailed explanation of the variation.  Remember, the RFP specifications are considered the minimum standards and the only acceptable deviations from the specifications must call for responses in excess of those specified and must be explained in detail in the proposal.

APPENDIX E – Company Proposal Response Grid

| A | B | C |
| --- | --- | --- |
| RFP Section | Company agrees with content of the RFP and will comply with the minimum specifications. YES / NO | Company is offering services above minimum. YES / NO (List Cost In Dollars) |
| 1 Introduction |  |  |
| 2 Profile of Municipality |  |  |
| 3 General Responsibilities of Municipality / ORPTS 3.1 Municipality |  |  |
| 3.2 ORPTS |  |  |
| 4 Project Requirements/Contractor Responsibilities 4.1 Project Management |  |  |
| 4.2 Project Timetable |  |  |
| 4.3 Public Information |  |  |
| 4.4 Local Staff Training |  |  |
| 4.5 Data Processing |  |  |
| 4.6 Tax Map Data |  |  |
| 4.7 Property owner Inquiry |  |  |
| 4.8 Subject Inventory Data Collection |  |  |
| 4.8.4 File Creation and Maintenance |  |  |
| 4.9 Sales Inventory Collection and File Creation |  |  |
| 4.10 Data Edits |  |  |
| 4.11 Valuation |  |  |
| 4.12 Field Review |  |  |
| 4.13 Assessor Value Review |  |  |
| 4.14 Assessment Disclosure Processing |  |  |
| 4.15 Informal Review Process |  |  |
| 4.16 Value Change Notice |  |  |
| 4.17 Formal Defense of Values |  |  |
| 4.18 Project Status Control |  |  |
| 4.19 Submissions for State Aid/Value Verification |  |  |
| 4.20 Mass Mailings and Postage |  |  |
| 4.21 Data Entry |  |  |
| 4.22 Valuation Documentation |  |  |
| 4.23 Post Reassessment Option |  |  |
| 5 Data Security |  |  |
| 6 Contractor Project Staffing |  |  |
| 7 Deliverable Products |  |  |
| 8 Payment Schedule and Penalty |  |  |
| 9 Contractual Requirements |  |  |

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #1

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- PROJECT COMMENCEMENT AND TIMETABLE

- PUBLIC INFORMATION COMMENCEMENT

- PHOTOGRAPHY/IMAGE OPTION

- DATA COLLECTION TRAINING

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ALL PHASES OF PROJECT TO THIS DATE

(Local Staff has been fully trained in all phases of the project completed to date.)

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE AS NEEDED

_________________________________			________________________________

Project Administrator		Date			Project Director		       Date

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #2

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- DATA COLLECTION

- SUBJECT FILE CREATION

- SALES FILE CREATION

- SALES VALIDATION AND VERIFICATION

- SALES VERIFICATION MAILER APPROVAL

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ABOVE PHASES OF PROJECT

(Local Staff has been fully trained in all phases of the project completed to date.)

- PUBLIC INFORMATION DELIVERABLES AS APPLICABLE

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE

________________________________	           		______________________________

Project Administrator		Date			Project Director	 	       Date

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #3

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- PROPERTY DESCRIPTION REPORT / DATA MAILER

- PRODUCTION IN RESPONSE TO PROPERTY DESCRIPTION REPORTS / DATA MAILERS

- INCOME & EXPENSE QUESTIONNAIRE APPROVAL AND TRANSMITTAL

- VALUATION FILE EDITING

- VALUATION TESTING

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ABOVE PHASES OF PROJECT

(Local Staff has been fully trained in all phases of the project completed to date.)

- PUBLIC INFORMATION DELIVERABLES AS APPLICABLE

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE

_________________________________			_______________________________

Project Administrator		Date			Project Director		       Date

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #4

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- VALUATION PRODUCTION

- FIELD REVIEW OF VALUES

- ASSESSOR’S VALUE REVIEW WITH CONTRACTOR

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ABOVE PHASES OF PROJECT

(Local Staff has been fully trained in all phases of the project completed to date.)

- PUBLIC INFORMATION DELIVERABLES AS APPLICABLE

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE

________________________________	           		______________________________

Project Administrator		Date			Project Director		       Date

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #5

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- UPDATE VALUES ON FILE

- ASSESSOR’S RECALCULATIONS OF EXEMPTIONS

- VERIFICATION OF ALL VALUES BY CONTRACTOR

- PROPERTY OWNER ASSESSMENT DISCLOSURE NOTICE PRODUCTION AND TAX SHIFT ANALYSIS, IF APPLICABLE [See guidance language for 4.14 Assessment disclosure processing / tax shift analysis.]

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ABOVE PHASES OF PROJECT

(Local Staff has been fully trained in all phases of the project completed to date.)

- PUBLIC INFORMATION DELIVERABLES AS APPLICABLE

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE

_________________________________ 		_______________________________

Project Administrator		Date			Project Director		      Date

APPENDIX F – Assessor’s Sign-off Documents

MUNICIPALITY SIGN OFF DOCUMENT #6

The project administrator and contractor have discussed the progress of the reassessment project for the Town/City of XXXX.  The RFP sections have been completed and the necessary deliverables have been provided to the Town/City relative to:

- ASSESSMENT DISCLOSURE MAILING

- INFORMAL REVIEW MEETINGS AND FIELD RELATED ACTIVITIES

- VALUE CHANGE NOTICES PRODUCTION

- TENTATIVE ASSESSMENT ROLL FILING

- PROJECT DELIVERABLES TO THE ASSESSOR

- LOCAL CAPACITY BUILDING ASSOCIATED WITH ABOVE PHASES OF PROJECT

(Local Staff has been fully trained in all phases of the project completed to date.)

- PUBLIC INFORMATION DELIVERABLES AS APPLICABLE

- RPS OR RPS COMPATIBLE FILES OF MUNICIPAL DATA (ASSESSMENT, INVENTORY, SALES, SALES INVENTORY) AND OTHER PROJECT DOCUMENTATION FOR LOCAL QUALITY CONTROL AND ORPTS’ PROJECT VERIFICATION HAVE BEEN MADE AVAILABLE

_________________________________			_______________________________

Project Administrator		Date			Project Director		       Date

APPENDIX G – Sample Forms Preferred by Municipality

- I&E Form(s) (Online Form Possibility?)

- Schedule of Costs Form(s) (Online Form Possibility?)

- Sample Public Relations Program [All public relations materials should be approved by the municipality prior to use]

- Sales Questionnaire and/or Suggested Process (Online Form Possibility?)

- Sample Performance Standards

  - Example – Connecticut standards – muni to develop their own)

- USPAP Compliant Documentation Format (Online Format Possibility?)

  - The IAAO Mass Appraisal Revaluation Template (attached) can assist your assessing jurisdiction document that USPAP minimum requirements are being met for reassessment. Documenting your reassessment promotes professionalism, transparency, and provides reference material readily available with the details about your reassessment.

[Municipality should determine which of these documents, if any, or others, should be included.]

Attachment: Volume 9 - Opinions of Counsel SBEA No. 4

Assessor (powers and duties) (entry upon real property) - Real Property Tax Law, §§500,501:

An assessor should not enter on private property and take measurements or photographs without first securing the permission of the land owner.

We have been asked whether an assessor has the right to enter on private property for purposes of making an assessment. This is a difficult problem which we have discussed in two prior opinions (7 Op.Counsel SBEA No. 19 and 2 Op.Counsel SBEA No. 78).

An assessor is charged with the duty of preparing an assessment roll (Real Property Tax Law, §504(1)). Individualized, personal viewing of each parcel of land by an assessor is not expressly required by the Real Property Tax Law (Bertholf v. Cisco, 72 Misc.2d 901,339 N.Y.S.2d 798 (Sup.Ct., Sullivan Co., 1973), affd, 45 A.D.2d 787,357 N.Y.S.2d 1023 (3d Dept. 1974)). However, sections 500 and 501 of the Real Property Tax Law require each assessor to prepare, maintain and make available assessment inventories. These inventories must include the name of the property owner, tax map land parcel number, property description, physical characteristics of the improvements to the parcel that are necessary to value the parcel by at least one of the standard appraisal methods, and exemption status (9 NYCRR 190-1.2).

As a general rule, real property is private, and the owner is entitled to exclusive possession thereof. The U.S. Constitution, Fourth Amendment prohibition against unreasonable searches and seizures has been applied to administrative inspections of private and commercial property. Thus, a landowner can deny access to property, even to government regulators such as health, building and fire inspectors. Accordingly, a warrant may be required for specific administrative inspection of private property. An entrance or intrusion upon the land, without a warrant, can result in a trespass.

The Supreme Court has identified numerous factors relevant in determining whether a warrant is required for a specific administrative inspection of premises (e.g., an assessor's entry on private property for the purpose of determining an assessment for that property). Administrative inspections of pervasively regulated industries (i.e., the liquor industry, interstate traffic in firearms and federal inspections of mines) have been held to be permissible without the necessity of a warrant (See Colonade Catering Corp. v. United States, 397 U.S. 72, 90 S.Ct. 774, 25 L.Ed.2d 60 (1970); United States v. Biswell, 406 U.S. 311, 92 S.Ct. 1593, 32 L.Ed.2d 87 (1972); Marshall v. Barlow's, Inc., 436 U.S. 307,98 S.Ct. 1816,56 L.Ed.2d 305 (1978); Donovan v. Dewey, 452 U.S. 594,101 S.Ct. 2534,69 L.Ed.2d 262 (1981)). A warrantless administrative inspection of premises may also occur when the imposition of a warrant requirement would impair the efficiency of a legislative scheme which authorizes the inspection (United States v. Biswell, 406 U.S. 311, 92 S.Ct. 1593, 32 L.Ed.2d 87 (1972); Marshall v. Barlow's, Inc., 436 U.S. 307, 98 S.Ct. 1816, 56 L.Ed.2d 305 (1978)). A warrant has also been held to be unnecessary for an administrative inspection of premises in an emergency situation Camara v. Municipal Court of San Francisco, 387 U.S. 523,87 S.Ct. 1727,18 L.Ed.2d 930 (1967); Michigan v. Tyler, 436 U.S. 499, 98 S.Ct. 1942, 56 L.Ed.2d 486 (1978)).

One additional factor that the Supreme Court has considered is the application of the "open fields" exception to the Fourth Amendment warrant requirement, to justify a warrantless administrative inspection of open land (Air Pollution Variance Bd. v. Western Alfalfa Corp., 416 U.S. 861, 94 S.Ct. 2114, 40 L.Ed.2d 607 (1974)). Accordingly, an administrative inspection requires a warrant unless the property is open to the public, i.e., the public is not excluded from the land. Even if the public is excluded from the property because the land is posted, the "open fields" exception to the Fourth Amendment search and seizure protection might be applied. An individual may not demand privacy for activities conducted out of doors in fields, except in an area immediately surrounding the home (the curtilage) (Oliver v. United States, 466 U.S. 170, 104 S.Ct. 1735, 80 L.Ed.2d 214 (1984)). Fences or "No Trespassing" signs do not generally effectively bar the public from viewing open fields (Id. at 179).

For administrative searches that are subject to the Fourth Amendment warrant requirement, probable cause for the issuance of a warrant will exist if the reasonable legislative and administrative standards promulgated for conducting such an inspection are shown by the government to be satisfied with respect to the particular premises sought to be inspected. Probable cause to issue an inspection warrant will exist only if the decision to inspect is based on neutral criteria and there are broad legislative or administrative guidelines for such inspections, i.e., inspections to enforce municipal fire, health or housing codes (Marshall v. Barlow's Inc., 436 U.S. 307, 98 S.Ct. -1816, 56 L.Ed.2d 305 (1978); Michigan v. Tyler, 436 U.S. 499, 98 S.Q. 1942,56 L.Ed.2d 486 (1978)).

There are no legislative or administrative standards or guidelines promulgated for an assessor conducting inspections to determine real property tax assessments. Accordingly, compared to fire, health or building inspectors, in our opinion, assessors would be far less likely to demonstrate probable cause to obtain an inspection warrant.

An assessor should not enter on private property and take measurements or photographs without first securing the permission of the landowner. It is a relatively simple procedure for an assessor to identify himself to the landowner and request permission before entering private property. This would result in less confusion because the landowner would not be placed in a situation of discovering an uninvited, unknown person on his property.

Nevertheless, a property owner cannot be permitted to escape taxation by denying access to the assessor. The assessor must determine an assessed value, even when access to property is denied by a property owner. Under such circumstances, the assessment of the property (necessarily more of an estimate and less of a computation) can be based on any reasonable method which would aid the assessor, including descriptions of the property by third persons who have seen the property (2 Op. Counsel SBEA No. 78). If the property owner is dissatisfied with his assessment, he will need to present proof to the board of assessment review (or a court) that the assessor's estimate was inaccurate.

March 2,1989
Revised January 4,1990

Updated: July 05, 2012

Attachment: IAAO Mass Appraisal Revaluation Template (adapted)

[This is an IAAO developed template for a report by a vendor on the services / deliverables provided, as specified in the municipality’s RFP and contract.  Use of this format is not mandatory though it is a comprehensive way to ensure the municipality is left with documentation as to what was done by the vendor as part of the reassessment.]

Mass Appraisal Revaluation Outline

I.	Note to user: Items contained in this section should be boilerplate and not subject to change except when the underlying definitions, such as those contained in statutes change. Standard 6-8 refers to the items listed below. Also, Advisory Opinion 32 refers to ad valorem property tax appraisal and mass appraisal assignments.

- Identify client and intended users

The information necessary to make this determination is contained in USPAP Statement 9. Because the mass appraisal assignment may be spelled out in statutory or other legislative requirements, the appraiser should be aware of the discussions and conclusions contained in Statement 9. (e.g., Statement 9 concludes the appraiser must have communication with the client prior to accepting the assignment, and that the intended use and intended users are to be determined prior to acceptance of the assignment.)

- State the intended use

Mass appraisals are generally used for ad valorem property tax purposes, but may be used for other purposes. Ad valorem applications might include a statement such as “Use of this appraisal and its conclusions is limited to the administration of property taxes according to the governing laws of this jurisdiction.”

- State the effective date of the appraisal

- State the date of the report

The effective date of the appraisal establishes the context for the value opinion, while the date of the report indicates whether the perspective of the appraiser on the market and property as of the effective date of appraisal was prospective, current, or retrospective.

Statement 3 should be consulted concerning this issue, as ad valorem mass appraisals are generally retrospective value opinions.

- State the type and definition of value and cite the source

For ad valorem mass appraisal assignments, the definition of value is often defined and found in statute or case law.

- Disclose all assumptions, limiting conditions, and jurisdictional exceptions including any that result in deviation from recognized methods and techniques or that affect analyses, opinions, and conclusions.

For illustration, the following might commonly be found in a mass appraisal report for ad valorem property tax purposes:

- The properties were assumed to be free of any and all liens and encumbrances. Each property has also been appraised as though under responsible ownership and competent management.

- Surveys of the assessed properties have not been provided. We have relied upon tax maps and other materials in the course of estimating physical dimensions and the acreage associated with assessed properties.

- We assume the utilization of the land and any improvements is located within the boundaries of the property described.  It is assumed that there are no adverse easements or encroachments for any parcel that have not already been addressed in the mass appraisal.

- In the preparation of the mass appraisal, interior inspections have/have not been made of the parcels of property included in this report. All inspections are made from the exterior only. It is assumed that the condition of the interior of each property is similar to its exterior condition, unless the assessor has received additional information from qualified sources giving more specific detail about the interior condition.

- Property inspection dates will have ranged in time from both before and after the appraisal date. It is assumed that there has been no material change in condition from the latest property inspection, unless otherwise noted on individual property records retained in the assessor’s office.

- We assume that there are no hidden or unapparent conditions associated with the properties, subsoil, or structures, which would render the properties (land and/or improvements) more or less valuable.

- It is assumed that the properties and/or the landowners are in full compliance with all applicable federal, state, and local environmental regulations and laws.

- It is assumed that all applicable zoning and use regulations have been complied with.

- It is assumed that all required licenses, certificates of occupancy, consents, or other instruments of legislative or administrative authority from any private, local, state, or national government entity have been obtained for any use on which the value opinions contained within this report are based.

- We have not been provided a hazardous condition’s report, nor are we qualified to detect hazardous materials. Therefore, evidence of hazardous materials, which may or may not be present on a property, was not observed. As a result, the final opinion of value is predicated upon the assumption that there is no such material on any of the properties that might result in a loss, or change in value.

- Information, estimates, and opinions furnished to the appraisers and incorporated into the analysis and final report were obtained from sources assumed to be reliable, and a reasonable effort has been made to verify such information. However, no warranty is given for the reliability of this information.

- The Americans with Disabilities Act (ADA) became effective January 26, 1992. We have not made compliance surveys nor conducted a specific analysis of any property to determine if it conforms to the various detailed requirements identified in the ADA. It is possible that such a survey might identify nonconformity with one or more ADA requirements, which could lead to a negative impact on the value of the property(s). Because such a survey has not been requested and is beyond the scope of this appraisal assignment, we did not take into consideration adherence or non-adherence to ADA in the valuation of the properties addressed in this report.

- Possession of this report does not carry with it the right of reproduction, and disclosure of this report is governed by the rules and regulations of the ___________________________, and is subject to jurisdictional exception and the laws of _______________________.

- Disclose all extraordinary assumptions and/or hypothetical conditions.

- Identify the property rights appraised.

Comment: When the property rights to be appraised are specified in a statute or court ruling, the law must be referenced.

Due to uniformity, most jurisdictions utilize fee simple; however need to check legal obligations through statutes, rules, regulations, etc….

II.	This is the body of the report that will change with each mass appraisal.

A.	Describe the appraisal assignment dictated by either statutes or local practice. Describe the scope of work used to develop the appraisal; exclusion of the sales comparison approach, cost approach, or income approach must be explained.

Comment: Because intended users’ reliance on an appraisal may be affected by the scope of the work, the report must enable them to be properly informed and not misled. Sufficient information includes disclosure of research and analyses performed and might include disclosure of research and analyses not performed.

When any portion of the work involves significant mass appraisal assistance, the appraiser must describe the extent of that assistance. The signing appraiser must also state the name(s) of those providing the significant mass appraisal assistance in the certification, in accordance with Standards Rule 6-9.

The scope of work can be contained throughout the document and, therefore, does not require its own section. Its specificity should meet peer and client expectations.

Advisory Opinion 28 and 29 provide further discussion and guidance for an acceptable scope of work. The disclosure requirements apply to scope of work performed rather than the scope of work initially planned.

B.	Identify the properties to be appraised

This identification may include political boundaries, topography, classification, number and type of properties.

C.	When an opinion of highest and best use was developed, discuss how that opinion was determined;

Comment: The mass appraisal report must reference case law, statute, or public policy that describes highest and best use requirements. When actual use is the requirement, the report must discuss how use-value opinions were developed. The appraiser’s reasoning in support of the highest and best use opinion must be provided in the depth and detail required by its significance to the appraisal.

If not addressed in case law or statute, the four tests should be applied for an appropriate analysis:

- Physically possible

- Legally permissible

- Financially feasible

- Maximally productive

D.	Results of preliminary testing

Ratio studies including performance measures should be used to support the mass appraisal decision.

E.	Describe and justify the model specification considered, data requirements, and model(s) chosen.

Land Valuation

Model Specification

Describe which of the following approaches were utilized and why

Abstraction

Sales comparison

Allocation

Capitalization of ground rent

Land residual

Data Requirements:

Number of total sales and percentage of sales used

Sale date range

Data Collection Procedures:

What we have done is:

The characteristics that we can rely upon are:

The characteristics that may present data inaccuracy are:

Model Calibration (Describe calibration methods considered and chosen, the mathematical form of the final model)

Ratio study

Review of model coefficients

Review of model estimates

Individual value estimates

Model Validation

(Describe the appraisal performance tests used and the performance measures attained such as ratio studies, measures of central tendency, appraisal level and appraisal bias.)

Cost Approach

Model Specification

Describe the source of cost model

Data Requirements:

Data Collection Procedures:

What we have done is:

The characteristics that we can rely upon are:

The characteristics that may present data inaccuracy are:

Model Calibration

(Describe calibration methods considered and chosen, the mathematical form of the final model)

Ratio study

Review of model coefficients

Review of Model Estimates

Individual Value Estimates

Model Validation

(Describe the appraisal performance tests used and the performance measures attained such as ratio studies, measures of central tendency, appraisal level and appraisal bias.)

Sales Comparison Approach

Model Specification

Data Requirements:

Data Collection Procedures:

What we have done is:

The characteristics that we can rely upon are:

The characteristics that may present data inaccuracy are:

Model Calibration

(Describe calibration methods considered and chosen, the mathematical form of the final model)

Ratio study

Review of model coefficients

Review of model estimates

Individual value estimates

Model Validation

(Describe the appraisal performance tests used and the performance measures attained such as ratio studies, measures of central tendency, appraisal level and appraisal bias.)

Income Approach

Model Specification

Describe which of following models were used and why:

Direct capitalization

GIM

GRM

Yield capitalization

Data Requirements:

Data Collection Procedures:

What we have done is:

The characteristics that we can rely upon are:

The characteristics that may present data inaccuracy are:

Model Calibration

(Describe calibration methods considered and chosen, the mathematical form of the final model)

Ratio study

Review of model coefficients

Review of model estimates

Individual value estimates

Model Validation

(Describe the appraisal performance tests used and the performance measures attained such as ratio studies, measures of central tendency, appraisal level and appraisal bias.)

Comment: The appraiser must provide sufficient information to enable the client and intended users to have confidence that the process and procedures used conform to accepted methods and result in credible value conclusions. In the case of mass appraisal for ad valorem taxation, stability and accuracy are important to the creditability of value opinions. The report must include a discussion of the rationale for each model, the calibration techniques to be used, and the performance measures to be used.

- Final testing – similar to the preliminary only final

- Describe the reconciliation performed, in accordance with Standards Rule 6-7.

The reconciliation should clearly summarize the quantity and quality of data, the applicability and relevance of the approaches considered, and the methods and techniques employed to ensure accuracy (including recognized testing procedures).

“Considering the quantity and quality of data and the reliability of the various models as shown in the performance tests above, we have concluded that the ____________ approach is the best estimate of market value.”

- Public disclosure

Disclosure to the taxpaying public of values of individual properties should be administered through normal jurisdictional processes. The value in this report may change as a result of processes following that disclosure.

- Include a signed certification in accordance with Standards Rule 6-9;

I certify that, to the best of my knowledge and belief:

__	the statements of fact contained in this report are true and correct.

__	the reported analyses, opinions, and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professionally analyses, opinions, and conclusions.

__	I have no (or the specified) present or prospective interest in the property that is the subject of this report, and I have no (or the specified) personal interest with respect to the parties involved.

__	I have no bias with respect to any property that is the subject of this report or to the parties involved with this assignment.

__	Any services regarding the subject performed by the appraiser within the three year period immediately preceding acceptance of the assignment, as an appraiser or in any other capacity is identified in the body of the report.

__	my engagement in this assignment was not contingent upon developing or reporting predetermined results.

__	my compensation for completing this assignment is not contingent upon the reporting of a predetermined value or direction in value that favors the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.

__	my analyses, opinions, and conclusions were developed, and this report has been prepared, in conformity with the Uniform Standards of Professional Appraisal Practice.

__	I have (or have not) made a personal inspection of the properties that are the subject of this report. (If more than one person signs the report, this certification must clearly specify which individuals did and which individuals did not make a personal inspection of the appraised property.)

__	no one provided significant mass appraisal assistance to the person signing this certification. (If there are exceptions, the name of each individual providing significant mass appraisal assistance must be stated.)

Comment: The above certification is not intended to disturb an elected or appointed assessor’s work plans or oaths of office. A signed certification is an integral part of the appraisal report. An appraiser, who signs any part of the mass appraisal report, including a letter of transmittal, must also sign the certification.

See Standards Rule 6-9 for more discussion on this topic.

____________________, Assessor

Mass Appraisal Revaluation Template

20__ Mass Appraisal of __________________ for 20__ Property Taxes

  - Client and Intended Users:

    - This report is prepared for ___________________________. Other intended users include ____________________________; No one else may rely on this report for any purpose.

  - Intended Use:

    - Use of this appraisal and its conclusions is limited to the administration of property taxes according to the governing laws of this jurisdiction.

  - Effective Date of the Appraisal: ______________________

  - Date of Report: _____________

  - Type and Definition of Value:

  - Assumptions, Limiting Conditions, and Jurisdictional Exceptions:

  - Extraordinary Assumptions and/or Hypothetical Conditions:

  - Property Rights Appraised

  - Scope of Work:

    - (Describe the appraisal assignment dictated either by statutes or local practice. Describe the scope of work used to develop the appraisal; exclusion of the sales comparison approach, cost approach, or income approach must be explained.

    - There is no requirement for the scope of work description to be in a particular or separate section of the report.)

  - Identification of Properties:

  - Highest and Best Use:

  - Preliminary Testing Results:

  - Model Specifications Considered, Data Requirements, and Model(s) Chosen

    - Land Valuation:

      - Model Specification:

      - Model Calibration:

      - Model Validation:

    - Improved Property Valuation:

      - Cost Approach:

        - Model Specification:

        - Model Calibration:

        - Model Validation:

      - Sales Comparison Approach

        - Model Specification:

        - Model Calibration:

        - Model Validation:

      - Income Approach

        - Model Specification:

        - Model Calibration:

        - Model Validation:

  - Final Testing:

  - Reconciliation:

    - Final value determinations were based on a careful analysis of the quantity and quality of data available to each estimation approach as well as validation through the performance statistics produced at the conclusion of each of the approaches used and the final testing validation.

  - Public Disclosure

  - Certification:

I certify that, to the best of my knowledge and belief:

__	 the statements of fact contained in this report are true and correct.

__	the reported analyses, opinions, and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions, and conclusions.

__	I have no (or the specified) present or prospective interest in the property that is the subject of this report, and I have no (or the specified) personal interest with respect to the property.

__	any services regarding the subject performed by the appraiser within the three year period immediately preceding acceptance of the assignment, as an appraiser or in any other capacity is identified in the body of the report.

__	I have no bias with respect to any property that is the subject of this report or to the parties involved with this assignment.

__	my engagement in this assignment was not contingent upon developing or reporting predetermined results.

__	my compensation for completing this assignment is not contingent upon the reporting of a predetermined value or direction in value that favors the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.

__	my analyses, opinions, and conclusions were developed, and this report has been prepared, in conformity with the Uniform Standards of Professional Appraisal Practice.

__	I have (or have not) made a personal inspection of the properties that are the subject of this report. (If more than one person signs the report, this certification must clearly specify which individuals did and which individuals did not make a personal inspection of the appraised property.)

__	no one provided significant mass appraisal assistance to the person signing this certification. (If there are exceptions, the name of each individual providing significant mass appraisal assistance are shown below.)

Signature:________________________________________________

Date:_______________________

Individuals providing significant mass appraisal assistance and work performed:

___________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________